## Kontrak
No. | KONTRAK | Start Date | End Date | Cut Off (SO) | PLANED DAYS | TIME GONE (Days) | TIME GONE % | STATUS | Ket. | PROGRESS FINANCE | PROGRESS ACTUAL | Nilai Kontrak 2023-2024 | Realisasi On 2023-2024 | Realisasi On 2025 | Non Realisasi | % Realisasi | % Non Realisasi |  | No. | KONTRAK | Start Date | End Date | Ket.
35 | 002/SPK/VI/2023 - KONTRAK JASA PAJAK | 2023-06-26 | 2024-02-26 | 2025-04-12 | 245 | 656 | 0% | NON ACTIVE | INCA & FIRMA RAJAWALI |  | 100% |  |  |  | 0 | 0% | 0% | [6 empty] | %percentage |  | Total Project | %percentage | Total Project
36 | 003/MKU-03/BAPP/INA/08/23 - BAPP MKU | 2023-07-17 | 2023-07-28 | 2025-04-12 | 11 | 635 | 0% | NON ACTIVE | INCA & MIPCON |  | 100% | 658 | 658 |  | 0 | 100% | 0% | 1 | 1 | 014/INA01/VI/2024-S | 2024-06-11 | 2025-09-11 | INCA & AVK = PENUNJUKAN | -100% | 1 | 16 | Below 30% | 16
1 | 002/INA02/2023L-C - Perjanjian Kerja (Kontrak) PT. INA _ PT ASR I | 2023-08-07 | 2024-03-30 | 2025-04-12 | 236 | 614 | 0% | NON ACTIVE | INCA & PT. ASR I |  | 100% | 3006 | 3006 |  | 0 | 100% | 0% | 1 | 2 | 012/INA01/V/2024-S | 2024-06-12 |  | INCA & TBA = PENUNJUKAN | 30% | 2 | 4 | 30% s.d 50% | 4
2 | 002/INA02/2023L-C - Perjanjian Kerja (Kontrak) PT. INA _ PT ASR II | 2023-08-07 | 2024-03-30 | 2025-04-12 | 236 | 614 | 0% | NON ACTIVE | INCA & PT. ASR II |  | 100% |  |  |  | 0 | 0% | 0% | 1 | 3 | 031/INA01/IX/2024-S | 2024-09-09 | 2025-05-15 | INCA & EBS = PENUNJUKAN | 50% | 3 | 7 | 50% s.d 80% | 7
34 | 001/MKU-03/BAST/INA/08/23 - BAST MKU | 2023-08-10 | 2023-08-10 | 2025-04-12 | 0 | 611 | 0% | NON ACTIVE | INCA & MIPCON |  | 100% |  |  |  | 0 | 0% | 0% | 1 | [5 empty] | 80% | 4 | 6 | 80% s.d 100% | 6
3 | 003/INA02/2023L-C - JASA PENYUSUNAN UKL UPL | 2023-08-22 | 2024-02-28 | 2025-04-12 | 190 | 599 | 0% | NON ACTIVE | INCA & PT. ENVITEK |  | 100% | 863 | 604 |  | 259 | 69.99% | 30.01% | 1 | [5 empty] | 100% | 5 | 3 | 100% Above | 3
32 | Sewa rumah sumbawa | 2023-09-01 | 2025-09-01 | 2025-04-12 | 731 | 589 | 80.57% | ACTIVE | INCA & ADY TULUS (RUMAH SUMBAWA) |  |  | 408 | 408 |  | 0 | 100% | 0% | 1 | [5 empty] | 500% | 6 | 0
4 | 004/INA02/2023L-C = INCA & ABB | 2023-10-01 | 2025-10-01 | 2025-04-12 | 731 | 559 | 76.47% | ACTIVE | INCA ABB |  |  | 9206 | 673 |  | 8533 | 7.31% | 92.69% | 4
28 | 028/INA02/II/2025/L-C = ADENDUM INCA & KSO PDS (1B) | 2023-10-01 | 2025-04-12 | 2025-04-12 | 559 | 559 | 100% | ACTIVE ADENDUM | INCA & KSO PDS (1B) |  |  | 10935 | 2187 |  | 8748 | 20% | 80% | 3 | [5 empty] | NON ACTIVE | 12 | 0%
5 | 005/INA02/2023L-C = INCA & ATK | 2023-11-20 | 2025-03-20 | 2025-04-12 | 486 | 509 | 104.7% | ACTIVE | INCA & ATK | [5 empty] | 0 | 0% | 0% | 5 | [5 empty] | ACTIVE | 18 | 58.97%
6 | 006/INA06/X/2023-S = INCA & ATK | 2023-12-26 | 2025-03-20 | 2025-04-12 | 450 | 473 | 0% | NON ACTIVE | INCA & ATK |  | 100% |  |  |  | 0 | 0% | 0% | 5 | [5 empty] | ACTIVE ADENDUM | 6 | 77.31%
7 | 006/INA02/2024L-C Perjanjian Kerja (Kontrak) Jasa Pengurusan PBG dan SLF | 2024-01-23 | 2025-04-23 | 2025-04-12 | 456 | 445 | 97.59% | ACTIVE | INCA & GEI | [5 empty] | 0 | 0% | 0% | 1
25 | 025/INA02/I/2025-L-C Pengurusan PBG dan SLF | 2024-01-23 | 2025-10-23 | 2025-04-12 | 639 | 445 | 69.64% | ACTIVE ADENDUM | INCA & GEI |  |  | 406 | 223 |  | 183 | 54.93% | 45.07% | 4
26 | 026/INA02/I/2025-L-C Pengurusan ABT dan Izin Operasional | 2024-01-30 | 2025-06-30 | 2025-04-12 | 517 | 438 | 84.72% | ACTIVE ADENDUM | INCA & GEI |  |  | 456 | 159 |  | 297 | 34.87% | 65.13% | 3
9 | 007/INA07/I/2024-S = Jasa Pendampingan & Pengawasan Pembangunan ATK | 2024-02-01 | 2025-07-30 | 2025-04-12 | 545 | 436 | 80% | ACTIVE ADENDUM | INCA & ATK = ADENDUM |  |  | 2710 | 1283 |  | 1427 | 47.34% | 52.66% | 4
10 | 008/INA02/VI/2024L-C Perjanjian Kerja INA dengan AVK | 2024-06-11 | 2025-09-11 | 2025-04-12 | 457 | 305 | 66.74% | ACTIVE | INCA & AVK |  |  | 6716 | 2687 |  | 4029 | 40.01% | 59.99% | 4
8 | 007/INA02/VI/2024L-C = INCA & TBA | 2024-06-12 | 2026-02-12 | 2025-04-12 | 610 | 304 | 49.84% | ACTIVE | INCA & TBA |  |  | 8306 | 6152 |  | 2154 | 74.07% | 25.93% | 3
30 | Surat Perjanjian Kerja 536/LMATS-SPK/VI/2024 | 2024-07-01 | 2026-06-30 | 2025-04-12 | 729 | 285 | 39.09% | ACTIVE | INCA & LMATS |  |  | 67 | 14 |  | 53 | 20.9% | 79.1% | 2
11 | 009/INA02/VIII/2024L-C = INCA & PDM 1A | 2024-07-05 | 2025-08-05 | 2025-04-12 | 396 | 281 | 70.96% | ACTIVE | INCA & PDM 1 A | [5 empty] | 0 | 0% | 0% | 2
33 | 001/03/LGL/IMI/VII/23 - Perjanjian Sewa Ruko Drupadi | 2024-08-01 | 2026-07-31 | 2025-04-12 | 729 | 254 | 34.84% | ACTIVE | INCA & IMI (RUKO DRUPADI) |  |  | 360 | 360 |  | 0 | 100% | 0% | 3
12 | 010/INA02/IX/2024L-C PKS PDM 1B | 2024-08-12 | 2025-04-12 | 2025-04-12 | 243 | 243 | 100% | ACTIVE | INCA & PDM 1 B | [5 empty] | 0 | 0% | 0% | 2
13 | 012/INA02/X/2024L-C Perjanjian Kerja Swadaya Warga dengan PT EBS | 2024-09-10 | 2025-02-15 | 2025-04-12 | 158 | 214 | 0% | NON ACTIVE | INCA & EBS |  | 100% |  |  |  | 0 | 0% | 0% | 5
18 | 018/INA02/XI/2024 L-C Addendum Pekerjaan Swadaya Warga | 2024-09-18 | 2025-05-19 | 2025-04-12 | 243 | 206 | 84.77% | ACTIVE | INCA & EBS = ADENDUM | 70% | 70.14% | 2571 | 1286 |  | 1285 | 50.02% | 49.98% | 1
17 | 017/INA02/X/2024 L-C Addendum Pekerjaan Tambak Udang Tahap 1B (PDM) | 2024-10-01 | 2025-07-12 | 2025-04-12 | 284 | 193 | 67.96% | ACTIVE | INCA & PDM = ADENDUM 1B | [5 empty] | 0 | 0% | 0% | 4
14 | 013/INA02/X/2024L-C - Perjanjian Sewa Menyewa rumah Lunyuk | 2024-10-09 | 2025-06-10 | 2025-04-12 | 244 | 185 | 75.82% | ACTIVE | INCA & ESTER (RUMAH LUNYUK) |  |  | 18 | 18 |  | 0 | 100% | 0% | 3
15 | 015/INA02/X/2024L-C -SPK AUDIT Laporan Keuangan | 2024-10-18 | 2024-12-31 | 2025-04-12 | 74 | 176 | 0% | NON ACTIVE | INCA & KAP (AUDIT) |  | 100% | 65 | 65 |  | 0 | 100% | 0% | 3
16 | 016/INA02/XI/2024L-C Jasa Pendampingan Kegiatan Program Perusahaan dan Sosial Mapping | 2024-10-24 | 2027-12-31 | 2025-04-12 | 1163 | 170 | 14.62% | ACTIVE | INCA & LDS |  |  | 1846 | 554 |  | 1292 | 30.01% | 69.99% | 1
31 | B/497/XI/2024 - Perjanjian Kerjasama INA & LANAL | 2024-11-28 | 2027-12-31 | 2025-04-12 | 1128 | 135 | 11.97% | ACTIVE | INCA & LANAL | [5 empty] | 0 | 0% | 0% | 1
19 | 019/INA02/XII/2024 L-C Jasa Pengurusan ABT dan Izin Operasional | 2024-12-10 | 2025-03-30 | 2025-04-12 | 110 | 123 | 0% | NON ACTIVE | INCA & GEI |  | 100% |  |  |  | 0 | 0% | 0% | 1
20 | 020/INA02/XII/2024 L-C IZIN LUAT | 2024-12-12 | 2025-06-30 | 2025-04-12 | 200 | 121 | 60.5% | ACTIVE | INCA & PT. ENVITEK |  |  | 1139 | 1139 |  | 0 | 100% | 0% | 1
21 | 021/INA02/XII/2024-L-C Perjanjian Penambahan Daya Listrik 97.000 Va | 2024-12-20 | 2024-02-20 | 2025-04-12 | -304 | 113 | 0% | NON ACTIVE | INCA & ADT |  | 100% |  |  |  | 0 | 0% | 0% | 3
29 | 029/INA02/II/2025-L-C Addendum Perjanjian Kerja (Ko_250311_200241 (1) | 2024-12-20 | 2025-04-20 | 2025-04-12 | 121 | 113 | 93.39% | ACTIVE ADENDUM | INCA & ADT |  |  | 198 | 191 |  | 7 | 96.46% | 3.535% | 1
22 | 022/INA02/XII/2024-L-C Perjanjian Sewa Menyewa Mobil | 2025-01-06 | 2027-01-06 | 2025-04-12 | 730 | 96 | 13.15% | ACTIVE | INCA & CV ALFI RENT CAR | [5 empty] | 0 | 0% | 0% | 4
23 | 023/INA02/I/2025 L-C Jasa Pengadaan Konsumsi | 2025-01-06 | 2027-03-30 | 2025-04-12 | 813 | 96 | 11.81% | ACTIVE | INCA & LDS | [5 empty] | 0 | 0% | 0% | 1
24 | 024/INA02/I/2025-L-C Perjanjian Kerja (Kontrak) Jasa Aktuaria Arya Bagiastra | 2025-01-09 | 2025-02-08 | 2025-04-12 | 30 | 93 | 0% | NON ACTIVE | INCA & AKTUARIA |  | 100% |  |  |  | 0 | 0% | 0% | 1
27 | 027/INA01/II/2025/L-C = ADENDUM INCA & KSO PDS (1A) | 2025-02-06 | 2025-08-05 | 2025-04-12 | 180 | 65 | 36.11% | ACTIVE ADENDUM | INCA & KSO PDS (1A) |  |  | 165987 | 42090 |  | 123897 | 25.36% | 74.64% | 1
2
12
Non Active
Contract
18
Active
Contract
6
Active Addendum
Summary Project Progress
Below 30% =
30% s.d 50% =
50% s.d 80% =
80% s.d 100% =
100% up =
16
Project
Project
Project
Project
Project
4
7
6
3
DASHBOARD PERFORMANCE KONTRAK

## DASHBOARD
PROJECT TASK LIST
PROJECT 1 A | 3
PROJECT 1 B | ALL PROJECT
0 | ALL DOCUMENT
PROJECT | NOMOR DOKUMEN | JENIS PEKERJAAN | AREA PEKERJAAN | SUB AREA PEKERJAAN | PRIORITY | START | PLAN END | CUTT OF (SO) | % COMPLETE | Project Start | Days to Start | Complete | Incomplete | Slippage | Plan Days
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | IPAL | LOW | 2024-09-09 | 2025-04-27 | 2025-04-12 | 20.58% | 2024-07-05 | 66 | 47.334 | 182.666 | -15 | 230
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | POWE HOUSE | LOW | 2025-04-07 | 2025-06-23 | 2025-04-12 | 0.45% | 2024-07-05 | 276 | 0.3465 | 76.6535 | -72 | 77
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESEARCH CENTRE ROOM | LOW | 2025-04-07 | 2025-06-22 | 2025-04-12 | 8.15% | 2024-07-05 | 276 | 6.194 | 69.806 | -71 | 76
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESERVOIR SEA WATER INTAKE | LOW | 2025-02-10 | 2025-03-09 | 2025-04-12 | 20.19% | 2024-07-05 | 220 | 5.4513 | 21.5487 | 34 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | AIR BERSIH | HIGH | 2024-07-08 | 2025-08-10 | 2025-04-12 | 84.6% | 2024-07-05 | 3 | 336.708 | 61.292 | -120 | 398
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | GALIAN & TIMBUNAN PIPA | LOW | 2025-04-07 | 2025-04-20 | 2025-04-12 | 0% | 2024-07-05 | 276 | 0 | 13 | -8 | 13
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | SEA WATER | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-04-12 | 28.98% | 2024-07-05 | 276 | 7.8246 | 19.1754 | -22 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | OFFSHORE AREA | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | LOW | 2025-02-10 | 2025-03-09 | 2025-04-12 | 0.98% | 2024-07-05 | 220 | 0.2646 | 26.7354 | 34 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | CONTROL ROOM (4 UNIT) | LOW | 2025-02-10 | 2025-04-27 | 2025-04-12 | 0% | 2024-07-05 | 220 | 0 | 76 | -15 | 76
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | GALIAN & TIM BUNAN PIPA (4 AREA) | LOW | 2025-05-05 | 2025-06-29 | 2025-04-12 | 0% | 2024-07-05 | 304 | 0 | 55 | -78 | 55
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | MAIN POND (12 UNIT) | MEDIUM | 2024-07-08 | 2025-06-08 | 2025-04-12 | 26.15% | 2024-07-05 | 3 | 87.6025 | 247.3975 | -57 | 335
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | NURSERY POND (4 unit) | LOW | 2024-12-16 | 2025-06-22 | 2025-04-12 | 16.6% | 2024-07-05 | 164 | 31.208 | 156.792 | -71 | 188
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | OPERATOR HOUSE (2 UNIT) | LOW | 2025-04-07 | 2025-06-15 | 2025-04-12 | 0% | 2024-07-05 | 276 | 0 | 69 | -64 | 69
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | PROBIOTIK P[OND (4 UNIT) | LOW | 2025-01-13 | 2025-03-09 | 2025-04-12 | 7.68% | 2024-07-05 | 192 | 4.224 | 50.776 | 34 | 55
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | SKIMMER POND (4 UNIT) | MEDIUM | 2025-01-13 | 2025-02-09 | 2025-04-12 | 25.32% | 2024-07-05 | 192 | 6.8364 | 20.1636 | 62 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | DEEPWELL PUMP ROOM (DWP) | HIGH | 2024-11-11 | 2025-02-09 | 2025-04-12 | 99.97% | 2024-07-05 | 129 | 89.973 | 0.027 | 62 | 90
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | POWER HOUSE & WEEKLY TANK | LOW | 2024-10-21 | 2025-05-04 | 2025-04-12 | 12.03% | 2024-07-05 | 108 | 23.4585 | 171.5415 | -22 | 195
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUPMP ROOM SWI | LOW | 2025-01-13 | 2025-02-09 | 2025-04-12 | 0% | 2024-07-05 | 192 | 0 | 27 | 62 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | RESEARCH CENTER ROOM | LOW | 2025-04-28 | 2025-05-11 | 2025-04-12 | 0% | 2024-07-05 | 297 | 0 | 13 | -29 | 13
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | HIGH | 2024-07-05 | 2025-09-03 | 2025-04-12 | 72.02% | 2024-07-05 | 0 | 306.085 | 118.915 | -144 | 425
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | LAND GRADING GALIAN & BUANGAN | LAND GRADING GALIAN & BUANGAN | HIGH | 2024-08-11 | 2025-01-12 | 2025-04-12 | 78.77% | 2024-07-05 | 37 | 121.3058 | 32.6942 | 90 | 154
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | PLATFORM RESEARCH CENTER ROOM | LOW | 2024-12-16 | 2025-06-15 | 2025-04-12 | 9.69% | 2024-07-05 | 164 | 17.5389 | 163.4611 | -64 | 181
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | LOW | 2025-05-26 | 2025-06-15 | 2025-04-12 | 0% | 2024-07-05 | 325 | 0 | 20 | -64 | 20
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PAGAR PANEL | PAGAR PANEL | MEDIUM | 2024-08-26 | 2025-05-04 | 2025-04-12 | 29.53% | 2024-07-05 | 52 | 74.1203 | 176.8797 | -22 | 251
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE IPAL & PANEN | LOW | 2025-05-05 | 2025-06-01 | 2025-04-12 | 19.45% | 2024-07-05 | 304 | 5.2515 | 21.7485 | -50 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-04-12 | 28.07% | 2024-07-05 | 276 | 7.5789 | 19.4211 | -22 | 27
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | LOW | 2025-03-10 | 2025-04-08 | 2025-04-12 | 12.46% | 2024-07-05 | 248 | 3.6134 | 25.3866 | 4 | 29
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN MASUK | LOW | 2024-09-30 | 2025-02-09 | 2025-04-12 | 0% | 2024-07-05 | 87 | 0 | 132 | 62 | 132
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEMBERSIHAN LAHAN | PEMBERSIHAN LAHAN | LOW | 2024-07-05 | 2024-08-25 | 2025-04-12 | (blank) | 2024-07-05 | 0 | 0 | 51 | 230 | 51
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | CONTROL ROOM & BLOWER (4 unit) | LOW | 2025-02-10 | 2025-04-13 | 2025-04-12 | 0% | 2024-07-05 | 220 | 0 | 62 | -1 | 62
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | IPAL | MEDIUM | 2024-07-22 | 2025-05-11 | 2025-04-12 | 42.8% | 2024-07-05 | 17 | 125.404 | 167.596 | -29 | 293 | SUB AREA PEKERJAAN | All
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | NURSERY POND (4 unit) | LOW | 2024-12-16 | 2025-06-22 | 2025-04-12 | 0% | 2024-07-05 | 164 | 0 | 188 | -71 | 188
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | OPERATOR HOUSE (2 unit) | LOW | 2025-02-10 | 2025-04-20 | 2025-04-12 | 0% | 2024-07-05 | 220 | 0 | 69 | -8 | 69
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | POND (12 unit) | LOW | 2024-07-22 | 2025-06-22 | 2025-04-12 | 1.21% | 2024-07-05 | 17 | 4.0535 | 330.9465 | -71 | 335
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | SKIMER POND (4 unit) | LOW | 2024-10-21 | 2025-02-16 | 2025-04-12 | 0% | 2024-07-05 | 108 | 0 | 118 | 55 | 118
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | SEA WATER INTAKE | SEA WATER INTAKE | MEDIUM | 2024-09-23 | 2024-12-22 | 2025-04-12 | 45.72% | 2024-07-05 | 80 | 41.148 | 48.852 | 111 | 90
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DEEPWELL PUMP ROOM | LOW | 2024-08-26 | 2025-01-26 | 2025-04-12 | 0% | 2024-07-05 | 52 | 0 | 153 | 76 | 153
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | POWER HOUSE | LOW | 2025-01-20 | 2025-06-15 | 2025-04-12 | 0% | 2024-07-05 | 199 | 0 | 146 | -64 | 146
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE SWI | LOW | 2025-02-03 | 2025-03-09 | 2025-04-12 | 0% | 2024-07-05 | 213 | 0 | 34 | 34 | 34
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | RESEARCH CENTER ROOM | LOW | 2025-05-12 | 2025-06-22 | 2025-04-12 | 0% | 2024-07-05 | 311 | 0 | 41 | -71 | 41
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | LOW | 2025-02-24 | 2025-04-20 | 2025-04-12 | 0% | 2024-07-05 | 234 | 0 | 55 | -8 | 55
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | OPERATOR HOUSE (2 UNIT)‐ | LOW | 2024-12-23 | 2025-04-13 | 2025-04-12 | 0% | 2024-07-05 | 171 | 0 | 111 | -1 | 111
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | LOW | 2025-02-24 | 2025-04-27 | 2025-04-12 | 0% | 2024-07-05 | 234 | 0 | 62 | -15 | 62
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DEEP WELL PUMP ROOM | LOW | 2024-10-14 | 2025-03-09 | 2025-04-12 | 0% | 2024-07-05 | 101 | 0 | 146 | 34 | 146
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OPERATOR HOUSE 1 s/d 2 | LOW | 2025-02-17 | 2025-03-09 | 2025-04-12 | 0% | 2024-07-05 | 227 | 0 | 20 | 34 | 20
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | POWER HOUSE | LOW | 2024-12-23 | 2025-01-26 | 2025-04-12 | 10.56% | 2024-07-05 | 171 | 3.5904 | 30.4096 | 76 | 34
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | RESEARCH CENTER ROOM & SWI‐ | LOW | 2025-03-17 | 2025-08-03 | 2025-04-12 | 0% | 2024-07-05 | 255 | 0 | 139 | -113 | 139
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | GENERAL | GENERAL | LOW | 2025-01-13 | 2025-06-29 | 2025-04-12 | 4.78% | 2024-07-05 | 192 | 7.9826 | 159.0174 | -78 | 167
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | GENERAL AREA POND | LOW | 2025-02-10 | 2025-05-11 | 2025-04-12 | 21.91% | 2024-07-05 | 220 | 19.719 | 70.281 | -29 | 90
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | LOW | 2024-12-16 | 2025-08-10 | 2025-04-12 | 0% | 2024-07-05 | 164 | 0 | 237 | -120 | 237
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY FEMALE | LOW | 2025-09-01 | 2025-08-24 | 2025-04-12 | 0% | 2024-08-01 | 396 | 0 | -8 | -134 | -8
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY MALE | LOW | 2025-09-01 | 2025-09-30 | 2025-04-12 | 0% | 2024-08-01 | 396 | 0 | 29 | -171 | 29
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FAMILY STAFF HOUSE | LOW | 2025-09-22 | 2025-09-30 | 2025-04-12 | 0% | 2024-08-01 | 417 | 0 | 8 | -171 | 8
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FEED WAREHOUSE | LOW | 2025-07-07 | 2025-07-27 | 2025-04-12 | 0% | 2024-08-01 | 340 | 0 | 20 | -106 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GARDU HUB | LOW | 2025-06-30 | 2025-07-13 | 2025-04-12 | 0% | 2024-08-01 | 333 | 0 | 13 | -92 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GAZEBOO | LOW | 2025-07-07 | 2025-08-03 | 2025-04-12 | 0% | 2024-08-01 | 340 | 0 | 27 | -113 | 27
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | KANTIN | LOW | 2025-08-25 | 2025-09-14 | 2025-04-12 | 0% | 2024-08-01 | 389 | 0 | 20 | -155 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | LABORATORIUM | LOW | 2025-09-01 | 2025-09-30 | 2025-04-12 | 0% | 2024-08-01 | 396 | 0 | 29 | -171 | 29
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | MOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OFFICE | LOW | 2025-07-07 | 2025-07-20 | 2025-04-12 | 0% | 2024-08-01 | 340 | 0 | 13 | -99 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | PUMP HOUSE | LOW | 2025-07-28 | 2025-08-24 | 2025-04-12 | 0% | 2024-08-01 | 361 | 0 | 27 | -134 | 27
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WEIGHT HOUSE | LOW | 2025-06-16 | 2025-06-29 | 2025-04-12 | 0% | 2024-08-01 | 319 | 0 | 13 | -78 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WORKSHOP | LOW | 2025-08-11 | 2025-08-31 | 2025-04-12 | 0% | 2024-08-01 | 375 | 0 | 20 | -141 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | GUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | PRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | VVIP HOUSE | LOW | 2025-09-01 | 2025-09-21 | 2025-04-12 | 0% | 2024-08-01 | 396 | 0 | 20 | -162 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY FEMALE | LOW | 2025-07-07 | 2025-05-31 | 2025-04-12 | 12.52% | 2024-08-01 | 340 | -4.632 | -32.368 | -49 | -37
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY MALE | LOW | 2025-06-30 | 2025-09-07 | 2025-04-12 | 0% | 2024-08-01 | 333 | 0 | 69 | -148 | 69
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FAMILY STAFF HOUSE | LOW | 2025-07-07 | 2025-09-30 | 2025-04-12 | 0% | 2024-08-01 | 340 | 0 | 85 | -171 | 85
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FEED WAREHOUSE | LOW | 2025-05-19 | 2025-06-06 | 2025-04-12 | 0% | 2024-08-01 | 291 | 0 | 18 | -55 | 18
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GARDU HUB | LOW | 2025-06-02 | 2025-07-13 | 2025-04-12 | 0% | 2024-08-01 | 305 | 0 | 41 | -92 | 41
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GAZEBOO (BY VENDOR) | LOW | 2025-06-23 | 2025-07-06 | 2025-04-12 | 0% | 2024-08-01 | 326 | 0 | 13 | -85 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | KANTIN | LOW | 2025-06-16 | 2025-08-17 | 2025-04-12 | 17.34% | 2024-08-01 | 319 | 10.7491 | 51.2509 | -127 | 62
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | LABORATORIUM | LOW | 2025-07-21 | 2025-08-24 | 2025-04-12 | 0% | 2024-08-01 | 354 | 0 | 34 | -134 | 34
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MAIN GATE | LOW | 2025-06-16 | 2025-07-20 | 2025-04-12 | 0% | 2024-08-01 | 319 | 0 | 34 | -99 | 34
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | OFFICE | LOW | 2025-06-16 | 2025-08-03 | 2025-04-12 | 14.33% | 2024-08-01 | 319 | 6.8806 | 41.1194 | -113 | 48
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE | LOW | 2025-05-19 | 2025-07-27 | 2025-04-12 | 0% | 2024-08-01 | 291 | 0 | 69 | -106 | 69
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | TPS | LOW | 2025-06-30 | 2025-08-31 | 2025-04-12 | 0% | 2024-08-01 | 333 | 0 | 62 | -141 | 62
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WEIGHT HOUSE | LOW | 2025-06-09 | 2025-07-27 | 2025-04-12 | 0% | 2024-08-01 | 312 | 0 | 48 | -106 | 48
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WORKSHOP | LOW | 2025-06-23 | 2024-08-10 | 2025-04-12 | 0% | 2024-08-01 | 326 | 0 | -317 | 245 | -317
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | GUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | PRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | VVIP HOUSE | LOW | 2025-07-28 | 2025-09-30 | 2025-04-12 | 0% | 2024-08-01 | 361 | 0 | 64 | -171 | 64
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY FEMALE | LOW | 2025-07-14 | 2025-07-20 | 2025-04-12 | 0% | 2024-08-01 | 347 | 0 | 6 | -99 | 6
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY MALE | LOW | 2025-07-07 | 2025-07-27 | 2025-04-12 | 0% | 2024-08-01 | 340 | 0 | 20 | -106 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | FAMILY STAFF HOUSE | LOW | 2025-07-28 | 2025-08-17 | 2025-04-12 | 0% | 2024-08-01 | 361 | 0 | 20 | -127 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 1 | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | KANTIN | LOW | 2025-07-14 | 2025-08-03 | 2025-04-12 | 0% | 2024-08-01 | 347 | 0 | 20 | -113 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | LABORATORIUM | LOW | 2025-07-28 | 2025-09-07 | 2025-04-12 | 0% | 2024-08-01 | 361 | 0 | 41 | -148 | 41
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | MOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | OFFICE | LOW | 2025-06-23 | 2025-07-06 | 2025-04-12 | 0% | 2024-08-01 | 326 | 0 | 13 | -85 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER FACILITY AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-04-12 | 0% | 2024-08-01 | 298 | 0 | 13 | -57 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER POND AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-04-12 | 0% | 2024-08-01 | 298 | 0 | 13 | -57 | 13
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | GUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | PRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | VVIP HOUSE | LOW | 2025-08-04 | 2025-08-24 | 2025-04-12 | 0% | 2024-08-01 | 368 | 0 | 20 | -134 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY FEMALE | MEDIUM | 2025-04-28 | 2025-08-17 | 2025-04-12 | 31.23% | 2024-08-01 | 270 | 34.665 | 76.335 | -127 | 111
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY MALE | LOW | 2024-10-28 | 2025-08-10 | 2025-04-12 | 7.166% | 2024-08-01 | 88 | 20.4948 | 265.5052 | -120 | 286
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FAMILY STAFF HOUSE | LOW | 2025-04-21 | 2025-08-24 | 2025-04-12 | 7.187% | 2024-08-01 | 263 | 8.9844 | 116.0156 | -134 | 125
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FEED WAREHOUSE | LOW | 2025-04-15 | 2025-06-08 | 2025-04-12 | 23.93% | 2024-08-01 | 257 | 12.9203 | 41.0797 | -57 | 54
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GARDU HUB | LOW | 2025-04-15 | 2025-05-17 | 2025-04-12 | 11.04% | 2024-08-01 | 257 | 3.5327 | 28.4673 | -35 | 32
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GAZEBOO | LOW | 2025-06-02 | 2025-06-22 | 2025-04-12 | 16.11% | 2024-08-01 | 305 | 3.2215 | 16.7785 | -71 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD TOWER | MEDIUM | 2025-04-21 | 2025-06-15 | 2025-04-12 | 28.55% | 2024-08-01 | 263 | 15.7029 | 39.2971 | -64 | 55
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | KANTIN | MEDIUM | 2025-04-21 | 2025-07-20 | 2025-04-12 | 43.4% | 2024-08-01 | 263 | 39.0592 | 50.9408 | -99 | 90
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | LABORATORIUM | LOW | 2025-04-15 | 2025-07-27 | 2025-04-12 | 8.637% | 2024-08-01 | 257 | 8.8961 | 94.1039 | -106 | 103
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MAIN GATE | LOW | 2025-04-28 | 2025-08-22 | 2025-04-12 | 0% | 2024-08-01 | 270 | 0 | 116 | -132 | 116
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | OFFICE | MEDIUM | 2025-04-15 | 2025-07-20 | 2025-04-12 | 40.78% | 2024-08-01 | 257 | 39.148 | 56.852 | -99 | 96
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUMP HOUSE | LOW | 2025-05-05 | 2025-07-13 | 2025-04-12 | 9.932% | 2024-08-01 | 277 | 6.8534 | 62.1466 | -92 | 69
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | TPS | LOW | 2025-05-05 | 2025-08-10 | 2025-04-12 | 6.221% | 2024-08-01 | 277 | 6.0343 | 90.9657 | -120 | 97
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | LOW | 2025-05-05 | 2025-05-25 | 2025-04-12 | 17.44% | 2024-08-01 | 277 | 3.4875 | 16.5125 | -43 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | LOW | 2025-05-05 | 2025-05-25 | 2025-04-12 | 17.44% | 2024-08-01 | 277 | 3.4875 | 16.5125 | -43 | 20
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WEIGHT HOUSE | MEDIUM | 2025-05-05 | 2025-07-13 | 2025-04-12 | 30.74% | 2024-08-01 | 277 | 21.2107 | 47.7893 | -92 | 69
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WORKSHOP | HIGH | 2025-04-28 | 2025-07-27 | 2025-04-12 | 79.93% | 2024-08-01 | 270 | 71.9326 | 18.0674 | -106 | 90
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | (blank) | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | GUEST HOUSE | LOW | 2024-08-12 | 2025-07-13 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 335 | -92 | 335
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | PRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | VVIP HOUSE | LOW | 2025-04-15 | 2025-08-31 | 2025-04-12 | 8.854% | 2024-08-01 | 257 | 12.218 | 125.782 | -141 | 138
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
ALL PROJECT
ALL DOCUMENT
14%
Summary Progress
15%
Project 1A
Project 1B
SUB AREA PEKERJAAN
464
Durasi Kontrak
(days)
Sisa Durasi
12
(days)

## BASE DATA (wajib update)
NO | KONTRAK | NOMOR DOKUMEN & NO. KONTRAK | JENIS PEKERJAAN | AREA PEKERJAAN | SUB AREA PEKERJAAN | CONCATE PEKERJAAN | PRIORITY | START | PLAN END | ACTUAL END | % COMPLETE | STATUS | Project Start | Days to Start | Complete (Yang sudah complete dalam satuan hari) | Incomplete (sisa HK) | Slippage | Plan Days | SISA DURASI KONTRAK | BOBOT
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN STRUKTURGENERAL | HIGH | 2024-07-05 | 2025-09-03 | 2025-08-31 | 75.34% | Dalam Proses | 2024-07-05 | 0 | 320.195 | 104.805 | -3 | 425 | -28 | 3.8286 | 0 | LOW
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEMBERSIHAN LAHAN | PEMBERSIHAN LAHAN | PROJECT 1 A PEKERJAAN STRUKTURPEMBERSIHAN LAHAN | LOW | 2024-07-05 | 2024-08-25 | 2025-08-31 |  | Selesai | 2024-07-05 | 0 | 0 | 51 | 371 | 51 | 0 | 0 | 0.25 | MEDIUM
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | LAND GRADING GALIAN & BUANGAN | LAND GRADING GALIAN & BUANGAN | PROJECT 1 A PEKERJAAN STRUKTURLAND GRADING GALIAN & BUANGAN | HIGH | 2024-08-11 | 2025-01-12 | 2025-08-31 | 78.78% | Dalam Proses | 2024-07-05 | 37 | 121.3212 | 32.6788 | 231 | 154 | -262 | 1.8587 | 0.6 | HIGH
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN MASUK | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN MASUK | LOW | 2024-09-30 | 2025-02-09 | 2025-08-31 | 0% | Tunda | 2024-07-05 | 87 | 0 | 132 | 203 | 132 | -234 | 0.79195 | 1 | HIGH
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | LOW | 2025-03-10 | 2025-04-08 | 2025-08-31 | 12.46% | Tunda | 2024-07-05 | 248 | 3.6134 | 25.3866 | 145 | 29 | -176 | 1.8582
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE JALAN MASUK & KAWASAN | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-08-31 | 35.59% | Dalam Proses | 2024-07-05 | 276 | 9.6093 | 17.3907 | 119 | 27 | -150 | 0.4507
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE IPAL & PANEN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE IPAL & PANEN | LOW | 2025-05-05 | 2025-06-01 | 2025-08-31 | 19.87% | Tunda | 2024-07-05 | 304 | 5.3649 | 21.6351 | 91 | 27 | -122 | 6.4714
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PAGAR PANEL | PAGAR PANEL | PROJECT 1 A PEKERJAAN STRUKTURPAGAR PANEL | MEDIUM | 2024-08-26 | 2025-05-04 | 2025-08-31 | 51.64% | Tunda | 2024-07-05 | 52 | 129.6164 | 121.3836 | 119 | 251 | -150 | 2.1938
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | SEA WATER INTAKE | SEA WATER INTAKE | PROJECT 1 A PEKERJAAN STRUKTURSEA WATER INTAKE | MEDIUM | 2024-09-23 | 2024-12-22 | 2025-08-31 | 45.72% | Dalam Proses | 2024-07-05 | 80 | 41.148 | 48.852 | 252 | 90 | -283 | 1.4899
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | POND (12 unit) | PROJECT 1 A PEKERJAAN STRUKTURPOND (12 unit) | LOW | 2024-07-22 | 2025-06-22 | 2025-08-31 | 9.46% | Terlambat | 2024-07-05 | 17 | 31.691 | 303.309 | 70 | 335 | -101 | 33.0584
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | NURSERY POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURNURSERY POND (4 unit) | LOW | 2024-12-16 | 2025-06-22 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 164 | 0 | 188 | 70 | 188 | -101 | 1.8989
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | SKIMER POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURSKIMER POND (4 unit) | LOW | 2024-10-21 | 2025-02-16 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 108 | 0 | 118 | 196 | 118 | -227 | 0.61599
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | CONTROL ROOM & BLOWER (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURCONTROL ROOM & BLOWER (4 unit) | LOW | 2025-02-10 | 2025-04-13 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 220 | 0 | 62 | 140 | 62 | -171 | 0.42275
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | OPERATOR HOUSE (2 unit) | PROJECT 1 A PEKERJAAN STRUKTUROPERATOR HOUSE (2 unit) | LOW | 2025-02-10 | 2025-04-20 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 220 | 0 | 69 | 133 | 69 | -164 | 0.054312
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | IPAL | PROJECT 1 A PEKERJAAN STRUKTURIPAL | MEDIUM | 2024-07-22 | 2025-05-11 | 2025-08-31 | 43.85% | Dalam Proses | 2024-07-05 | 17 | 128.4805 | 164.5195 | 112 | 293 | -143 | 0.74005
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURRESEARCH CENTER ROOM | LOW | 2025-04-28 | 2025-05-11 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 297 | 0 | 13 | 112 | 13 | -143 | 0.17748
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | DEEPWELL PUMP ROOM (DWP) | PROJECT 1 A PEKERJAAN STRUKTURDEEPWELL PUMP ROOM (DWP) | HIGH | 2024-11-11 | 2025-02-09 | 2025-08-31 | 99.97% | Tunda | 2024-07-05 | 129 | 89.973 | 0.027 | 203 | 90 | -234 | 0.03925
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUPMP ROOM SWI | PROJECT 1 A PEKERJAAN STRUKTURPUPMP ROOM SWI | LOW | 2025-01-13 | 2025-02-09 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 192 | 0 | 27 | 203 | 27 | -234 | 0.049777
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | POWER HOUSE & WEEKLY TANK | PROJECT 1 A PEKERJAAN STRUKTURPOWER HOUSE & WEEKLY TANK | LOW | 2024-10-21 | 2025-05-04 | 2025-08-31 | 15.77% | Tunda | 2024-07-05 | 108 | 30.7515 | 164.2485 | 119 | 195 | -150 | 1.9867
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | PLATFORM RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURPLATFORM RESEARCH CENTER ROOM | LOW | 2024-12-16 | 2025-06-15 | 2025-08-31 | 12.9% | Belum Mulai | 2024-07-05 | 164 | 23.349 | 157.651 | 77 | 181 | -108 | 8.0827
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | PROJECT 1 A PEKERJAAN STRUKTURTANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | LOW | 2025-05-26 | 2025-06-15 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 325 | 0 | 20 | 77 | 20 | -108 | 0.048862
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTURCONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | LOW | 2025-02-24 | 2025-04-20 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 234 | 0 | 55 | 133 | 55 | -164 | 0.22891
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | OPERATOR HOUSE (2 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTUROPERATOR HOUSE (2 UNIT)‐ | LOW | 2024-12-23 | 2025-04-13 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 171 | 0 | 111 | 140 | 111 | -171 | 0.074967
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ARSITEKTURPOWER HOUSE | LOW | 2025-01-20 | 2025-06-15 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 199 | 0 | 146 | 77 | 146 | -108 | 0.41565
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURRESEARCH CENTER ROOM | LOW | 2025-05-12 | 2025-06-22 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 311 | 0 | 41 | 70 | 41 | -101 | 0.34221
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DEEPWELL PUMP ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURDEEPWELL PUMP ROOM | LOW | 2024-08-26 | 2025-01-26 | 2025-08-31 | 20.93% | Tunda | 2024-07-05 | 52 | 32.0229 | 120.9771 | 217 | 153 | -248 | 0.020404
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE SWI | PROJECT 1 A PEKERJAAN ARSITEKTURPUMP HOUSE SWI | LOW | 2025-02-03 | 2025-03-09 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 213 | 0 | 34 | 175 | 34 | -206 | 0.023371
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL | LOW | 2025-01-13 | 2025-06-29 | 2025-08-31 | 4.78% | Belum Mulai | 2024-07-05 | 192 | 7.9826 | 159.0174 | 63 | 167 | -94 | 2.9188
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | RESEARCH CENTER ROOM & SWI‐ | PROJECT 1 A PEKERJAAN ELEKTRIKALRESEARCH CENTER ROOM & SWI‐ | LOW | 2025-03-17 | 2025-08-03 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 255 | 0 | 139 | 28 | 139 | -59 | 0.11597
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | PROJECT 1 A PEKERJAAN ELEKTRIKALCONTROL ROOM & BLOWER HOUSE 1 s/d 4 | LOW | 2025-02-24 | 2025-04-27 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 234 | 0 | 62 | 126 | 62 | -157 | 0.081748
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OPERATOR HOUSE 1 s/d 2 | PROJECT 1 A PEKERJAAN ELEKTRIKALOPERATOR HOUSE 1 s/d 2 | LOW | 2025-02-17 | 2025-03-09 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 227 | 0 | 20 | 175 | 20 | -206 | 0.043968
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DEEP WELL PUMP ROOM | PROJECT 1 A PEKERJAAN ELEKTRIKALDEEP WELL PUMP ROOM | LOW | 2024-10-14 | 2025-03-09 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 101 | 0 | 146 | 175 | 146 | -206 | 0.012092
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ELEKTRIKALPOWER HOUSE | LOW | 2024-12-23 | 2025-01-26 | 2025-08-31 | 10.56% | Belum Mulai | 2024-07-05 | 171 | 3.5904 | 30.4096 | 217 | 34 | -248 | 2.2129
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | GENERAL AREA POND | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL AREA POND | LOW | 2025-02-10 | 2025-05-11 | 2025-08-31 | 21.91% | Belum Mulai | 2024-07-05 | 220 | 19.719 | 70.281 | 112 | 90 | -143 | 0.7164
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | PROJECT 1 A PEKERJAAN ELEKTRIKALPOND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | LOW | 2024-12-16 | 2025-08-10 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 164 | 0 | 237 | 21 | 237 | -52 | 2.7883
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | AIR BERSIH | PROJECT 1 A PEKERJAAN MEKANIKALAIR BERSIH | HIGH | 2024-07-08 | 2025-08-10 | 2025-08-31 | 84.6% | Dalam Proses | 2024-07-05 | 3 | 336.708 | 61.292 | 21 | 398 | -52 | 0.24445
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | SEA WATER | PROJECT 1 A PEKERJAAN MEKANIKALSEA WATER | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-08-31 | 33.68% | Belum Mulai | 2024-07-05 | 276 | 9.0936 | 17.9064 | 119 | 27 | -150 | 1.3834
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | GALIAN & TIMBUNAN PIPA | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIMBUNAN PIPA | LOW | 2025-04-07 | 2025-04-20 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 276 | 0 | 13 | 133 | 13 | -164 | 0.39134
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | POWE HOUSE | PROJECT 1 A PEKERJAAN MEKANIKALPOWE HOUSE | LOW | 2025-04-07 | 2025-06-23 | 2025-08-31 | 0.45% | Belum Mulai | 2024-07-05 | 276 | 0.3465 | 76.6535 | 69 | 77 | -100 | 0.10778
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESEARCH CENTRE ROOM | PROJECT 1 A PEKERJAAN MEKANIKALRESEARCH CENTRE ROOM | LOW | 2025-04-07 | 2025-06-22 | 2025-08-31 | 8.15% | Belum Mulai | 2024-07-05 | 276 | 6.194 | 69.806 | 70 | 76 | -101 | 0.0082318
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | IPAL | PROJECT 1 A PEKERJAAN MEKANIKALIPAL | LOW | 2024-09-09 | 2025-04-27 | 2025-08-31 | 20.58% | Belum Mulai | 2024-07-05 | 66 | 47.334 | 182.666 | 126 | 230 | -157 | 0.063041
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESERVOIR SEA WATER INTAKE | PROJECT 1 A PEKERJAAN MEKANIKALRESERVOIR SEA WATER INTAKE | LOW | 2025-02-10 | 2025-03-09 | 2025-08-31 | 20.19% | Belum Mulai | 2024-07-05 | 220 | 5.4513 | 21.5487 | 175 | 27 | -206 | 0.035387
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | NURSERY POND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALNURSERY POND (4 UNIT) | LOW | 2024-12-16 | 2025-06-22 | 2025-08-31 | 23.01% | Belum Mulai | 2024-07-05 | 164 | 43.2588 | 144.7412 | 70 | 188 | -101 | 0.58542
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | MAIN POND (12 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALMAIN POND (12 UNIT) | MEDIUM | 2024-07-08 | 2025-06-08 | 2025-08-31 | 37.67% | Belum Mulai | 2024-07-05 | 3 | 126.1945 | 208.8055 | 84 | 335 | -115 | 18.9643
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | PROBIOTIK P[OND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALPROBIOTIK P[OND (4 UNIT) | LOW | 2025-01-13 | 2025-03-09 | 2025-08-31 | 7.68% | Belum Mulai | 2024-07-05 | 192 | 4.224 | 50.776 | 175 | 55 | -206 | 0.021883
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | SKIMMER POND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALSKIMMER POND (4 UNIT) | MEDIUM | 2025-01-13 | 2025-02-09 | 2025-08-31 | 44.63% | Belum Mulai | 2024-07-05 | 192 | 12.0501 | 14.9499 | 203 | 27 | -234 | 0.10434
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | CONTROL ROOM (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALCONTROL ROOM (4 UNIT) | LOW | 2025-02-10 | 2025-04-27 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 220 | 0 | 76 | 126 | 76 | -157 | 1.65
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | OPERATOR HOUSE (2 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALOPERATOR HOUSE (2 UNIT) | LOW | 2025-04-07 | 2025-06-15 | 2025-08-31 | 0% | Belum Mulai | 2024-07-05 | 276 | 0 | 69 | 77 | 69 | -108 | 0.014876
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | GALIAN & TIM BUNAN PIPA (4 AREA) | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIM BUNAN PIPA (4 AREA) | LOW | 2025-05-05 | 2025-06-29 | 2025-08-31 | 7.27% | Belum Mulai | 2024-07-05 | 304 | 3.9985 | 51.0015 | 63 | 55 | -94 | 0.067955
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | OFFSHORE AREA | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | PROJECT 1 A PEKERJAAN MEKANIKALTRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | LOW | 2025-02-10 | 2025-03-09 | 2025-08-31 | 0.98% | Belum Mulai | 2024-07-05 | 220 | 0.2646 | 26.7354 | 175 | 27 | -206 | 0.24341
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 BPEKERJAAN STRUKTURGENERAL | MEDIUM | 2024-08-12 | 2025-10-12 | 2025-08-31 | 58.09% | Dalam Proses | 2024-08-01 | 11 | 247.4634 | 178.5366 | -42 | 426 | 12 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-08-31 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -42 | 426 | 0 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN STRUKTURFEED WAREHOUSE | HIGH | 2025-04-15 | 2025-06-08 | 2025-08-31 | 100% | Dalam Proses | 2024-08-01 | 257 | 54 | 0 | 84 | 54 | -115 | 7.3157
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN STRUKTURLABORATORIUM | HIGH | 2025-04-15 | 2025-07-27 | 2025-08-31 | 85.97% | Dalam Proses | 2024-08-01 | 257 | 88.5491 | 14.4509 | 35 | 103 | -66 | 1.2678
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | HIGH | 2025-05-05 | 2025-05-25 | 2025-08-31 | 100% | Belum Mulai | 2024-08-01 | 277 | 20 | 0 | 98 | 20 | -129 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | HIGH | 2025-05-05 | 2025-05-25 | 2025-08-31 | 100% | Terlambat | 2024-08-01 | 277 | 20 | 0 | 98 | 20 | -129 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD TOWER | PROJECT 1 BPEKERJAAN STRUKTURGUARD TOWER | MEDIUM | 2025-04-21 | 2025-06-15 | 2025-08-31 | 29.82% | Dalam Proses | 2024-08-01 | 263 | 16.401 | 38.599 | 77 | 55 | -108 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN STRUKTURKANTIN | HIGH | 2025-04-21 | 2025-07-20 | 2025-08-31 | 99.27% | Dalam Proses | 2024-08-01 | 263 | 89.343 | 0.657 | 42 | 90 | -73 | 1.5819
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN STRUKTURFAMILY STAFF HOUSE | MEDIUM | 2025-04-21 | 2025-08-24 | 2025-08-31 | 25.73% | Dalam Proses | 2024-08-01 | 263 | 32.1625 | 92.8375 | 7 | 125 | -38 | 1.2842
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN STRUKTURWORKSHOP | HIGH | 2025-04-28 | 2025-07-27 | 2025-08-31 | 100% | Dalam Proses | 2024-08-01 | 270 | 90 | 0 | 35 | 90 | -66 | 6.1842
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN STRUKTURMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPUMP HOUSE | HIGH | 2025-05-05 | 2025-07-13 | 2025-08-31 | 85.83% | Dalam Proses | 2024-08-01 | 277 | 59.2227 | 9.7773 | 49 | 69 | -80 | 0.94074
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY FEMALE | HIGH | 2025-04-28 | 2025-08-17 | 2025-08-31 | 98.79% | Dalam Proses | 2024-08-01 | 270 | 109.6569 | 1.3431 | 14 | 111 | -45 | 1.2317
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY MALE | LOW | 2024-10-28 | 2025-08-10 | 2025-08-31 | 17.52% | Dalam Proses | 2024-08-01 | 88 | 50.1072 | 235.8928 | 21 | 286 | -52 | 4.3412
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN STRUKTURGAZEBOO | HIGH | 2025-06-02 | 2025-06-22 | 2025-08-31 | 100% | Terlambat | 2024-08-01 | 305 | 20 | 0 | 70 | 20 | -101 | 0.012874
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN STRUKTURGARDU HUB | LOW | 2025-04-15 | 2025-05-17 | 2025-08-31 | 12.41% | Dalam Proses | 2024-08-01 | 257 | 3.9712 | 28.0288 | 106 | 32 | -137 | 0.87756
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN STRUKTURWEIGHT HOUSE | HIGH | 2025-05-05 | 2025-07-13 | 2025-08-31 | 91.18% | Dalam Proses | 2024-08-01 | 277 | 62.9142 | 6.0858 | 49 | 69 | -80 | 5.6464
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN STRUKTUROFFICE | HIGH | 2025-04-15 | 2025-07-20 | 2025-08-31 | 100% | Dalam Proses | 2024-08-01 | 257 | 95.9992 | 0.000768 | 42 | 96 | -73 | 3.3921
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN STRUKTURTPS | HIGH | 2025-05-05 | 2025-08-10 | 2025-08-31 | 76.27% | Dalam Proses | 2024-08-01 | 277 | 73.9819 | 23.0181 | 21 | 97 | -52 | 1.1565
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN STRUKTURMAIN GATE | LOW | 2025-04-28 | 2025-08-22 | 2025-08-31 | 0.3225% | Dalam Proses | 2024-08-01 | 270 | 0.3741 | 115.6259 | 9 | 116 | -40 | 0.35948
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN STRUKTURGUEST HOUSE | LOW | 2024-08-12 | 2025-07-13 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 335 | 49 | 335 | -80 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURVVIP HOUSE | LOW | 2025-04-15 | 2025-08-31 | 2025-08-31 | 13.28% | Terlambat | 2024-08-01 | 257 | 18.3264 | 119.6736 | 0 | 138 | -31 | 7.3681
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ARSITEKTURLABORATORIUM | HIGH | 2025-07-21 | 2025-08-24 | 2025-08-31 | 70.68% | Belum Mulai | 2024-08-01 | 354 | 24.0312 | 9.9688 | 7 | 34 | -38 | 1.9262
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFEED WAREHOUSE | HIGH | 2025-05-19 | 2025-06-06 | 2025-08-31 | 84.15% | Terlambat | 2024-08-01 | 291 | 15.147 | 2.853 | 86 | 18 | -117 | 2.6948
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY MALE | LOW | 2025-06-30 | 2025-09-07 | 2025-08-31 | 14.46% | Terlambat | 2024-08-01 | 333 | 9.9774 | 59.0226 | -7 | 69 | -24 | 7.1456
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ARSITEKTURKANTIN | HIGH | 2025-06-16 | 2025-08-17 | 2025-08-31 | 81.53% | Dalam Proses | 2024-08-01 | 319 | 50.5486 | 11.4514 | 14 | 62 | -45 | 2.1251
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ARSITEKTURWORKSHOP | HIGH | 2025-06-23 | 2024-08-10 | 2025-08-31 | 91.21% | Terlambat | 2024-08-01 | 326 | -289.1357 | -27.8643 | 386 | -317 | -417 | 2.2141
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFAMILY STAFF HOUSE | LOW | 2025-07-07 | 2025-09-30 | 2025-08-31 | 7.58% | Terlambat | 2024-08-01 | 340 | 6.443 | 78.557 | -30 | 85 | -1 | 2.1434
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ARSITEKTURMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ARSITEKTUROFFICE | HIGH | 2025-06-16 | 2025-08-03 | 2025-08-31 | 87.19% | Dalam Proses | 2024-08-01 | 319 | 41.8512 | 6.1488 | 28 | 48 | -59 | 4.2092
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURWEIGHT HOUSE | HIGH | 2025-06-09 | 2025-07-27 | 2025-08-31 | 87.16% | Belum Mulai | 2024-08-01 | 312 | 41.8368 | 6.1632 | 35 | 48 | -66 | 0.67907
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GAZEBOO (BY VENDOR) | PROJECT 1 BPEKERJAAN ARSITEKTURGAZEBOO (BY VENDOR) | LOW | 2025-06-23 | 2025-07-06 | 2025-08-31 | 0% | Terlambat | 2024-08-01 | 326 | 0 | 13 | 56 | 13 | -87 | 0.37058
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPUMP HOUSE | HIGH | 2025-05-19 | 2025-07-27 | 2025-08-31 | 86.22% | Terlambat | 2024-08-01 | 291 | 59.4918 | 9.5082 | 35 | 69 | -66 | 0.46783
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY FEMALE | HIGH | 2025-07-07 | 2025-05-31 | 2025-08-31 | 71.13% | Dalam Proses | 2024-08-01 | 340 | -26.3181 | -10.6819 | 92 | -37 | -123 | 2.1434
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-08-31 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -42 | 426 | 0 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN ARSITEKTURTPS | MEDIUM | 2025-06-30 | 2025-08-31 | 2025-08-31 | 49.69% | Terlambat | 2024-08-01 | 333 | 30.8078 | 31.1922 | 0 | 62 | -31 | 0.6683
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN ARSITEKTURMAIN GATE | LOW | 2025-06-16 | 2025-07-20 | 2025-08-31 | 0.6845% | Dalam Proses | 2024-08-01 | 319 | 0.23273 | 33.7673 | 42 | 34 | -73 | 0.4509
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ARSITEKTURGARDU HUB | LOW | 2025-06-02 | 2025-07-13 | 2025-08-31 | 8.12% | Terlambat | 2024-08-01 | 305 | 3.3292 | 37.6708 | 49 | 41 | -80 | 0.47544
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURVVIP HOUSE | LOW | 2025-07-28 | 2025-09-30 | 2025-08-31 | 9.85% | Terlambat | 2024-08-01 | 361 | 6.304 | 57.696 | -30 | 64 | -1 | 7.4012
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN MEKANIKALLABORATORIUM | LOW | 2025-07-28 | 2025-09-07 | 2025-08-31 | 15.54% | Belum Mulai | 2024-08-01 | 361 | 6.3714 | 34.6286 | -7 | 41 | -24 | 0.1253
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Terlambat | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY MALE | LOW | 2025-07-07 | 2025-07-27 | 2025-08-31 | 6.99% | Terlambat | 2024-08-01 | 340 | 1.398 | 18.602 | 35 | 20 | -66 | 0.53564
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN MEKANIKALKANTIN | MEDIUM | 2025-07-14 | 2025-08-03 | 2025-08-31 | 30.08% | Terlambat | 2024-08-01 | 347 | 6.016 | 13.984 | 28 | 20 | -59 | 0.31366
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALFAMILY STAFF HOUSE | LOW | 2025-07-28 | 2025-08-17 | 2025-08-31 | 18.66% | Terlambat | 2024-08-01 | 361 | 3.732 | 16.268 | 14 | 20 | -45 | 0.15028
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN MEKANIKALMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN MEKANIKALOFFICE | MEDIUM | 2025-06-23 | 2025-07-06 | 2025-08-31 | 34.83% | Terlambat | 2024-08-01 | 326 | 4.5279 | 8.4721 | 56 | 13 | -87 | 0.16406
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY FEMALE | MEDIUM | 2025-07-14 | 2025-07-20 | 2025-08-31 | 43.1% | Terlambat | 2024-08-01 | 347 | 2.586 | 3.414 | 42 | 6 | -73 | 0.15028
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 1 | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Terlambat | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER POND AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER POND AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-08-31 | 8.48% | Terlambat | 2024-08-01 | 298 | 1.1024 | 11.8976 | 84 | 13 | -115 | 0.41311
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER FACILITY AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER FACILITY AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-08-31 | 8.48% | Terlambat | 2024-08-01 | 298 | 1.1024 | 11.8976 | 84 | 13 | -115 | 0.41311
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALVVIP HOUSE | LOW | 2025-08-04 | 2025-08-24 | 2025-08-31 | 23.98% | Belum Mulai | 2024-08-01 | 368 | 4.796 | 15.204 | 7 | 20 | -38 | 0.71591
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALVVIP HOUSE | MEDIUM | 2025-09-01 | 2025-09-21 | 2025-08-31 | 44.91% | Belum Mulai | 2024-08-01 | 396 | 8.982 | 11.018 | -21 | 20 | -10 | 1.1364
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ELEKTRIKALKANTIN | MEDIUM | 2025-08-25 | 2025-09-14 | 2025-08-31 | 48.92% | Terlambat | 2024-08-01 | 389 | 9.784 | 10.216 | -14 | 20 | -17 | 0.86889
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ELEKTRIKALLABORATORIUM | HIGH | 2025-09-01 | 2025-09-30 | 2025-08-31 | 60.95% | Terlambat | 2024-08-01 | 396 | 17.6755 | 11.3245 | -30 | 29 | -1 | 1.9102
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ELEKTRIKALOFFICE | MEDIUM | 2025-07-07 | 2025-07-20 | 2025-08-31 | 59.1% | Belum Mulai | 2024-08-01 | 340 | 7.683 | 5.317 | 42 | 13 | -73 | 2.3615
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ELEKTRIKALMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-08-31 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -42 | 426 | 0 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-08-31 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -42 | 426 | 12 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ELEKTRIKALWORKSHOP | MEDIUM | 2025-08-11 | 2025-08-31 | 2025-08-31 | 56.56% | Terlambat | 2024-08-01 | 375 | 11.312 | 8.688 | 0 | 20 | -31 | 1.2773
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFEED WAREHOUSE | MEDIUM | 2025-07-07 | 2025-07-27 | 2025-08-31 | 56.91% | Terlambat | 2024-08-01 | 340 | 11.382 | 8.618 | 35 | 20 | -66 | 1.3022
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY MALE | LOW | 2025-09-01 | 2025-09-30 | 2025-08-31 | 0% | Terlambat | 2024-08-01 | 396 | 0 | 29 | -30 | 29 | -1 | 2.2106
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALWEIGHT HOUSE | MEDIUM | 2025-06-16 | 2025-06-29 | 2025-08-31 | 52.31% | Terlambat | 2024-08-01 | 319 | 6.8003 | 6.1997 | 63 | 13 | -94 | 0.9409
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN ELEKTRIKALGAZEBOO | MEDIUM | 2025-07-07 | 2025-08-03 | 2025-08-31 | 30% | Belum Mulai | 2024-08-01 | 340 | 8.1 | 18.9 | 28 | 27 | -59 | 0.8322
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFAMILY STAFF HOUSE | LOW | 2025-09-22 | 2025-09-30 | 2025-08-31 | 0% | Terlambat | 2024-08-01 | 417 | 0 | 8 | -30 | 8 | -1 | 1.143
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY FEMALE | MEDIUM | 2025-09-01 | 2025-08-24 | 2025-08-31 | 51.34% | Terlambat | 2024-08-01 | 396 | -4.1072 | -3.8928 | 7 | -8 | -38 | 0.65729
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPUMP HOUSE | MEDIUM | 2025-07-28 | 2025-08-24 | 2025-08-31 | 51.61% | Terlambat | 2024-08-01 | 361 | 13.9347 | 13.0653 | 7 | 27 | -38 | 1.1354
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ELEKTRIKALGARDU HUB | MEDIUM | 2025-06-30 | 2025-07-13 | 2025-08-31 | 30% | Belum Mulai | 2024-08-01 | 333 | 3.9 | 9.1 | 49 | 13 | -80 | 0.45616
1 | PROJECT EBS | 012/INA02/IX/2024L-C | PEKERJAAN SWADAYA WARGA | FACILITY AREA | PRIVATE, GH, MOSQUE, POS 1 & 2 | PROJECT EBS PEKERJAAN SWADAYA WARGA PRIVATE, GH, MOSQUE, POS 1 & 2 | HIGH | 2024-09-10 | 2025-10-10 | 2025-10-10 | 100% | Done | 2024-09-10 | 0 | 395 | 0 | 0 | 395 | 10 | 1
2 | PROJECT EBS | 039/INA02/VI/2025/L-C | PEKERJAAN SWADAYA WARGA | FACILITY AREA | POS LANAL | PROJECT EBS PEKERJAAN SWADAYA WARGA POS LANAL | HIGH | 2025-06-23 | 2025-12-23 | 2025-12-23 | 63.29% | Dalam Proses | 2025-06-23 | 0 | 115.8134 | 67.1866 | 0 | 183 | 84 | 1
3 | PROJECT EBS | 062/INA02/IX/2025/L-C | PEKERJAAN SWADAYA WARGA | FACILITY AREA | PAGAR PANEL 372.5 M | PROJECT EBS PEKERJAAN SWADAYA WARGA PAGAR PANEL 372.5 M | HIGH | 2025-09-05 | 2025-10-05 | 2025-10-05 | 100% | Done | 2025-09-05 | 0 | 30 | 0 | 0 | 30 | 5 | 1
4 | PROJECT EBS | 061/INA02/IX/2025/L-C | PEKERJAAN SWADAYA WARGA | FACILITY AREA | PAGAR PANEL 310 M | PROJECT EBS PEKERJAAN SWADAYA WARGA PAGAR PANEL 310 M | MEDIUM | 2025-09-05 | 2025-11-05 | 2025-11-05 | 40% | Dalam Proses | 2025-09-05 | 0 | 24.4 | 36.6 | 0 | 61 | 36 | 1
5 | PROJECT EBS | 063/INA02/IX/2024L-C | PEKERJAAN SWADAYA WARGA | FACILITY AREA & PRIVATE AREA | DORMITORY MALE & VVIP HOUSE | PROJECT EBS PEKERJAAN SWADAYA WARGA DORMITORY MALE & VVIP HOUSE | LOW | 2025-09-05 | 2026-03-04 | 2026-03-04 | 0% | Dalam Proses | 2025-09-05 | 0 | 0 | 180 | 0 | 180 | 155 | 1
1 | PROJECT ADT | 040/INA02/VI/2025/L-C | PEKERJAAN ELEKTRIKAL | POWER HOUSE AREA | MV CUBICLE | PROJECT ADT PEKERJAAN ELEKTRIKAL MV CUBICLE | LOW | 2025-06-23 | 2025-12-23 | 2025-12-23 | 0% | Dalam Proses | 2025-06-23 | 0 | 0 | 183 | 0 | 183 | 84 | 1
2 | PROJECT ADT | 051/INA02/VIII/2025/L-C | PEKERJAAN ELEKTRIKAL | GENERAL | TRAFO 400,500 DAN 800 Kva | PROJECT ADT PEKERJAAN ELEKTRIKAL TRAFO 400,500 DAN 800 Kva | LOW | 2025-08-26 | 2026-02-26 | 2026-02-26 | 0% | Dalam Proses | 2025-08-26 | 0 | 0 | 184 | 0 | 184 | 149 | 1

## NILAI KONTRAK
CONTRACT MAPPING
In Mio (IDR) Include Tax
VENDOR | Nilai Kontrak 2023-2024 | Realisasi On 2023-2024 | Realisasi On 2025 | Non Realisasi | % Realisasi | % Non Realisasi | STATUS KONTRAK
PT Mipcon (Soil Test & Topografi) | 658 | 658 |  | 0 | 100% | 0% | CLOSED
PT ASR (GEO, FEED, DED) | 3006 | 3006 |  | 0 | 100% | 0% | CLOSED
PT ENVITEK (UKL, UPL, & LINGK.) | 1139 | 1139 |  | 0 | 100% | 0% | CLOSED
PT IIMI (SEWA KANTOR BALI) | 360 | 360 |  | 0 | 100% | 0% | CLOSED
ADI TULUS (SEWA KONTRAKAN SUMBAWA) | 408 | 408 |  | 0 | 100% | 0% | CLOSED
ESTER ( SEWA KONTRAKAN LUNYUK | 18 | 18 |  | 0 | 100% | 0% | CLOSED
KAP BUDIARTHA (AUDITOR) | 65 | 33 |  | 32 | 50.77% | 49.23% | PROGRESS
PT GEI ( PBG & SLF) | 406 | 223 |  | 183 | 54.93% | 45.07% | PROGRESS
PT ABB (JASA OPERATIONAL) | 9206 | 673 |  | 8533 | 7.31% | 92.69% | PROGRESS
PT AVK (GENSET) | 6716 | 2687 |  | 4029 | 40.01% | 59.99% | PROGRESS
PT EBS 1B (SWADAYA) | 2571 | 1286 |  | 1285 | 50.02% | 49.98% | PROGRESS
PT PDM TAHAP 1 A (FAS. UTAMA) | 165987 | 42090 |  | 123897 | 25.36% | 74.64% | PROGRESS
PT PDM TAHAP 1 B (FAS.PENUNJANG) | 10935 | 2187 |  | 8748 | 20% | 80% | PROGRESS
PT TBA (POMPA) | 8306 | 6152 |  | 2154 | 74.07% | 25.93% | PROGRESS
LMATS (KONSULTAN TAX) | 67 | 14 |  | 53 | 20.9% | 79.1% | PROGRESS
PT ATK (KONSULTAN PROJECT) | 2710 | 1283 |  | 1427 | 47.34% | 52.66% | PROGRESS
PT LDS (SOSIAL MAPING & HUMAS) | 1846 | 554 |  | 1292 | 30.01% | 69.99% | PROGRESS
PT EBS (FURNITURE) | 131 | 66 |  | 65 | 50.38% | 49.62% | PROGRESS
PT ENVITEK (IJIN KKPRL) | 863 | 604 |  | 259 | 69.99% | 30.01% | PROGRESS
PT AFNAN DEVA TEKNIK | 198 | 191 |  | 7 | 96.46% | 3.535% | PROGRESS
PT GEI (ABT & IJIN OPR) | 455 | 159 |  | 296 | 34.95% | 65.05% | PROGRESS
TOTAL | 216051 | 63791 | 0 | 152260 | 29.53% | 70.47% | 0

## PIVOT
PROJECT 1 A |  |  |  |  | now | 2025-09-30 08:45 |  | project srart | 2024-07-05 |  |  | 15.19% | [8 empty] | AREA PEKERJAAN | All |  | AREA PEKERJAAN | All
PROJECT 1 B |  |  |  |  | sisa durasi | 11.6351 | 464 | plan end | 2025-10-12 |  | 11.79% | 14.13% |  |  |  |  | -317 | -278 | [13 empty] | 0
[21 empty] | Sum of SISA DURASI KONTRAK |  |  | Count of SUB AREA PEKERJAAN |  | Sum of BOBOT |  |  | Sum of BOBOT
KONTRAK | NOMOR DOKUMEN & NO. KONTRAK | JENIS PEKERJAAN | AREA PEKERJAAN | SUB AREA PEKERJAAN | CONCATE PEKERJAAN | PRIORITY | STATUS | START | PLAN END | ACTUAL END | % COMPLETE | Project Start | Days to Start | Complete (Yang sudah complete dalam satuan hari) | Incomplete (sisa HK) | Slippage | Plan Days | SISA DURASI KONTRAK | BOBOT |  | KONTRAK | SUB AREA PEKERJAAN | Total | STATUS | Total | KONTRAK | SUB AREA PEKERJAAN | Total | KONTRAK | SUB AREA PEKERJAAN | Total
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | IPAL | PROJECT 1 A PEKERJAAN MEKANIKALIPAL | LOW | Belum Mulai | 2024-09-09 | 2025-04-27 | 2025-04-12 | 0.2058 | 2024-07-05 | 66 | 47.334 | 182.666 | -15 | 230 | -18 | 0.063041 | 0.012974 | PROJECT 1 A | AIR BERSIH | 88 | Belum Mulai | 47 | PROJECT 1 B | VVIP HOUSE | 16.6217 | PROJECT 1 A | POND (12 unit) | 33.0584
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | POWE HOUSE | PROJECT 1 A PEKERJAAN MEKANIKALPOWE HOUSE | LOW | Belum Mulai | 2025-04-07 | 2025-06-23 | 2025-04-12 | 0.0045 | 2024-07-05 | 276 | 0.3465 | 76.6535 | -72 | 77 | 40 | 0.10778 | 0.000485 | PROJECT 1 A | CONTROL ROOM (4 UNIT) | -18 | Dalam Proses | 37 | PROJECT 1 B | DORMITORY MALE | 14.233 | PROJECT 1 A | MAIN POND (12 UNIT) | 18.9643
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESEARCH CENTRE ROOM | PROJECT 1 A PEKERJAAN MEKANIKALRESEARCH CENTRE ROOM | LOW | Belum Mulai | 2025-04-07 | 2025-06-22 | 2025-04-12 | 0.0815 | 2024-07-05 | 276 | 6.194 | 69.806 | -71 | 76 | 39 | 0.0082318 | 0.00067089 | PROJECT 1 A | CONTROL ROOM & BLOWER (4 unit) | -32 | Selesai | 4 | PROJECT 1 B | FEED WAREHOUSE | 11.3127 | PROJECT 1 A | PLATFORM RESEARCH CENTER ROOM | 8.0827
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESERVOIR SEA WATER INTAKE | PROJECT 1 A PEKERJAAN MEKANIKALRESERVOIR SEA WATER INTAKE | LOW | Belum Mulai | 2025-02-10 | 2025-03-09 | 2025-04-12 | 0.2019 | 2024-07-05 | 220 | 5.4513 | 21.5487 | 34 | 27 | -67 | 0.035387 | 0.0071446 | PROJECT 1 A | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | -25 | Terlambat | 31 | PROJECT 1 B | OFFICE | 10.1269 | PROJECT 1 A | GENERAL | 6.7474
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | AIR BERSIH | PROJECT 1 A PEKERJAAN MEKANIKALAIR BERSIH | HIGH | Dalam Proses | 2024-07-08 | 2025-08-10 | 2025-04-12 | 0.846 | 2024-07-05 | 3 | 336.708 | 61.292 | -120 | 398 | 88 | 0.24445 | 0.20681 | PROJECT 1 A | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | -18 | Tunda | 7 | PROJECT 1 B | WORKSHOP | 9.6756 | PROJECT 1 A | PEKERJAAN DRAINASE IPAL & PANEN | 6.4714
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | GALIAN & TIMBUNAN PIPA | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIMBUNAN PIPA | LOW | Belum Mulai | 2025-04-07 | 2025-04-20 | 2025-04-12 | 0 | 2024-07-05 | 276 | 0 | 13 | -8 | 13 | -25 | 0.39134 | 0 | PROJECT 1 A | DEEP WELL PUMP ROOM | -67 |  |  | PROJECT 1 B | WEIGHT HOUSE | 7.2664 | PROJECT 1 A | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | 2.7883
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | SEA WATER | PROJECT 1 A PEKERJAAN MEKANIKALSEA WATER | MEDIUM | Belum Mulai | 2025-04-07 | 2025-05-04 | 2025-04-12 | 0.2898 | 2024-07-05 | 276 | 7.8246 | 19.1754 | -22 | 27 | -11 | 1.3834 | 0.40091 | PROJECT 1 A | DEEPWELL PUMP ROOM | -109 |  |  | PROJECT 1 B | LABORATORIUM | 5.2295 | PROJECT 1 A | POWER HOUSE | 2.6286
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | OFFSHORE AREA | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | PROJECT 1 A PEKERJAAN MEKANIKALTRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | LOW | Belum Mulai | 2025-02-10 | 2025-03-09 | 2025-04-12 | 0.0098 | 2024-07-05 | 220 | 0.2646 | 26.7354 | 34 | 27 | -67 | 0.24341 | 0.0023855 | PROJECT 1 A | DEEPWELL PUMP ROOM (DWP) | -95 |  |  | PROJECT 1 B | KANTIN | 4.8895 | PROJECT 1 A | NURSERY POND (4 unit) | 2.4844
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | CONTROL ROOM (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALCONTROL ROOM (4 UNIT) | LOW | Belum Mulai | 2025-02-10 | 2025-04-27 | 2025-04-12 | 0 | 2024-07-05 | 220 | 0 | 76 | -15 | 76 | -18 | 1.65 | 0 | PROJECT 1 A | GALIAN & TIM BUNAN PIPA (4 AREA) | 46 |  |  | PROJECT 1 B | FAMILY STAFF HOUSE | 4.7209 | PROJECT 1 A | PAGAR PANEL | 2.1938
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | GALIAN & TIM BUNAN PIPA (4 AREA) | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIM BUNAN PIPA (4 AREA) | LOW | Belum Mulai | 2025-05-05 | 2025-06-29 | 2025-04-12 | 0 | 2024-07-05 | 304 | 0 | 55 | -78 | 55 | 46 | 0.067955 | 0 | PROJECT 1 A | GALIAN & TIMBUNAN PIPA | -25 |  |  | PROJECT 1 B | DORMITORY FEMALE | 4.1827 | PROJECT 1 A | POWER HOUSE & WEEKLY TANK | 1.9867
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | MAIN POND (12 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALMAIN POND (12 UNIT) | MEDIUM | Belum Mulai | 2024-07-08 | 2025-06-08 | 2025-04-12 | 0.2615 | 2024-07-05 | 3 | 87.6025 | 247.3975 | -57 | 335 | 25 | 18.9643 | 4.9592 | PROJECT 1 A | GENERAL | 158 |  |  | PROJECT 1 B | PUMP HOUSE | 2.544 | PROJECT 1 A | LAND GRADING GALIAN & BUANGAN | 1.8587
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | NURSERY POND (4 unit) | PROJECT 1 A PEKERJAAN MEKANIKALNURSERY POND (4 UNIT) | LOW | Belum Mulai | 2024-12-16 | 2025-06-22 | 2025-04-12 | 0.166 | 2024-07-05 | 164 | 31.208 | 156.792 | -71 | 188 | 39 | 0.58542 | 0.09718 | PROJECT 1 A | GENERAL AREA POND | -4 |  |  | PROJECT 1 B | TPS | 1.8248 | PROJECT 1 A | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | 1.8582
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | OPERATOR HOUSE (2 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALOPERATOR HOUSE (2 UNIT) | LOW | Belum Mulai | 2025-04-07 | 2025-06-15 | 2025-04-12 | 0 | 2024-07-05 | 276 | 0 | 69 | -64 | 69 | 32 | 0.014876 | 0 | PROJECT 1 A | IPAL | -22 |  |  | PROJECT 1 B | GARDU HUB | 1.8092 | PROJECT 1 A | CONTROL ROOM (4 UNIT) | 1.65
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | PROBIOTIK P[OND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALPROBIOTIK P[OND (4 UNIT) | LOW | Belum Mulai | 2025-01-13 | 2025-03-09 | 2025-04-12 | 0.0768 | 2024-07-05 | 192 | 4.224 | 50.776 | 34 | 55 | -67 | 0.021883 | 0.0016806 | PROJECT 1 A | LAND GRADING GALIAN & BUANGAN | -123 |  |  | PROJECT 1 B | WATER TOWER 1 | 1.8072 | PROJECT 1 A | SEA WATER INTAKE | 1.4899
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | SKIMMER POND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALSKIMMER POND (4 UNIT) | MEDIUM | Belum Mulai | 2025-01-13 | 2025-02-09 | 2025-04-12 | 0.2532 | 2024-07-05 | 192 | 6.8364 | 20.1636 | 62 | 27 | -95 | 0.10434 | 0.026418 | PROJECT 1 A | MAIN POND (12 UNIT) | 25 |  |  | PROJECT 1 B | GUARD TOWER | 0.90362 | PROJECT 1 A | SEA WATER | 1.3834
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | DEEPWELL PUMP ROOM (DWP) | PROJECT 1 A PEKERJAAN STRUKTURDEEPWELL PUMP ROOM (DWP) | HIGH | Tunda | 2024-11-11 | 2025-02-09 | 2025-04-12 | 0.9997 | 2024-07-05 | 129 | 89.973 | 0.027 | 62 | 90 | -95 | 0.03925 | 0.039238 | PROJECT 1 A | NURSERY POND (4 unit) | 78 |  |  | PROJECT 1 B | GAZEBOO | 0.84508 | PROJECT 1 A | IPAL | 0.80309
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | POWER HOUSE & WEEKLY TANK | PROJECT 1 A PEKERJAAN STRUKTURPOWER HOUSE & WEEKLY TANK | LOW | Tunda | 2024-10-21 | 2025-05-04 | 2025-04-12 | 0.1203 | 2024-07-05 | 108 | 23.4585 | 171.5415 | -22 | 195 | -11 | 1.9867 | 0.239 | PROJECT 1 A | OPERATOR HOUSE (2 UNIT) | 32 |  |  | PROJECT 1 B | MAIN GATE | 0.81038 | PROJECT 1 A | PEKERJAAN PEKERASAAN JALAN MASUK | 0.79195
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUPMP ROOM SWI | PROJECT 1 A PEKERJAAN STRUKTURPUPMP ROOM SWI | LOW | Belum Mulai | 2025-01-13 | 2025-02-09 | 2025-04-12 | 0 | 2024-07-05 | 192 | 0 | 27 | 62 | 27 | -95 | 0.049777 | 0 | PROJECT 1 A | OPERATOR HOUSE 1 s/d 2 | -67 |  |  | PROJECT 1 B | WATER TOWER FACILITY AREA | 0.41311 | PROJECT 1 A | GENERAL AREA POND | 0.7164
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURRESEARCH CENTER ROOM | LOW | Belum Mulai | 2025-04-28 | 2025-05-11 | 2025-04-12 | 0 | 2024-07-05 | 297 | 0 | 13 | -29 | 13 | -4 | 0.17748 | 0 | PROJECT 1 A | OPERATOR HOUSE (2 unit) | -25 |  |  | PROJECT 1 B | WATER TOWER POND AREA | 0.41311 | PROJECT 1 A | SKIMER POND (4 unit) | 0.61599
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN STRUKTURGENERAL | HIGH | Dalam Proses | 2024-07-05 | 2025-09-03 | 2025-04-12 | 0.7202 | 2024-07-05 | 0 | 306.085 | 118.915 | -144 | 425 | 112 | 3.8286 | 2.7574 | PROJECT 1 A | OPERATOR HOUSE (2 UNIT)‐ | -32 |  |  | PROJECT 1 B | GAZEBOO (BY VENDOR) | 0.37058 | PROJECT 1 A | RESEARCH CENTER ROOM | 0.5197
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | LAND GRADING GALIAN & BUANGAN | LAND GRADING GALIAN & BUANGAN | PROJECT 1 A PEKERJAAN STRUKTURLAND GRADING GALIAN & BUANGAN | HIGH | Dalam Proses | 2024-08-11 | 2025-01-12 | 2025-04-12 | 0.7877 | 2024-07-05 | 37 | 121.3058 | 32.6942 | 90 | 154 | -123 | 1.8587 | 1.4641 | PROJECT 1 A | PAGAR PANEL | -11 |  |  | PROJECT 1 B | GUARD HOUSE 1 | 0 | PROJECT 1 A | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | 0.4507
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | PLATFORM RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURPLATFORM RESEARCH CENTER ROOM | LOW | Belum Mulai | 2024-12-16 | 2025-06-15 | 2025-04-12 | 0.0969 | 2024-07-05 | 164 | 17.5389 | 163.4611 | -64 | 181 | 32 | 8.0827 | 0.78321 | PROJECT 1 A | PEKERJAAN DRAINASE IPAL & PANEN | 18 |  |  | PROJECT 1 B | MOSQUE | 0 | PROJECT 1 A | CONTROL ROOM & BLOWER (4 unit) | 0.42275
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | PROJECT 1 A PEKERJAAN STRUKTURTANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | LOW | Belum Mulai | 2025-05-26 | 2025-06-15 | 2025-04-12 | 0 | 2024-07-05 | 325 | 0 | 20 | -64 | 20 | 32 | 0.048862 | 0 | PROJECT 1 A | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | -11 |  |  | PROJECT 1 B | PRIVATE HOUSE | 0 | PROJECT 1 A | GALIAN & TIMBUNAN PIPA | 0.39134
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PAGAR PANEL | PAGAR PANEL | PROJECT 1 A PEKERJAAN STRUKTURPAGAR PANEL | MEDIUM | Tunda | 2024-08-26 | 2025-05-04 | 2025-04-12 | 0.2953 | 2024-07-05 | 52 | 74.1203 | 176.8797 | -22 | 251 | -11 | 2.1938 | 0.64784 | PROJECT 1 A | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | -37 |  |  | PROJECT 1 B | GENERAL | 0 | PROJECT 1 A | AIR BERSIH | 0.24445
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE IPAL & PANEN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE IPAL & PANEN | LOW | Tunda | 2025-05-05 | 2025-06-01 | 2025-04-12 | 0.1945 | 2024-07-05 | 304 | 5.2515 | 21.7485 | -50 | 27 | 18 | 6.4714 | 1.2587 | PROJECT 1 A | PEKERJAAN PEKERASAAN JALAN MASUK | -95 |  |  | PROJECT 1 B | GUEST HOUSE | 0 | PROJECT 1 A | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | 0.24341
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE JALAN MASUK & KAWASAN | MEDIUM | Dalam Proses | 2025-04-07 | 2025-05-04 | 2025-04-12 | 0.2807 | 2024-07-05 | 276 | 7.5789 | 19.4211 | -22 | 27 | -11 | 0.4507 | 0.12651 | PROJECT 1 A | PEMBERSIHAN LAHAN | 0 |  |  | PROJECT 1 B | GUARD HOUSE 2 | 0 | PROJECT 1 A | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | 0.22891
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | LOW | Tunda | 2025-03-10 | 2025-04-08 | 2025-04-12 | 0.1246 | 2024-07-05 | 248 | 3.6134 | 25.3866 | 4 | 29 | -37 | 1.8582 | 0.23153 | PROJECT 1 A | PLATFORM RESEARCH CENTER ROOM | 32 | [5 empty] | PROJECT 1 A | RESEARCH CENTER ROOM & SWI‐ | 0.11597
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN MASUK | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN MASUK | LOW | Tunda | 2024-09-30 | 2025-02-09 | 2025-04-12 | 0 | 2024-07-05 | 87 | 0 | 132 | 62 | 132 | -95 | 0.79195 | 0 | PROJECT 1 A | POND (12 unit) | 39 | [5 empty] | PROJECT 1 A | POWE HOUSE | 0.10778
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEMBERSIHAN LAHAN | PEMBERSIHAN LAHAN | PROJECT 1 A PEKERJAAN STRUKTURPEMBERSIHAN LAHAN | LOW | Selesai | 2024-07-05 | 2024-08-25 | 2025-04-12 | (blank) | 2024-07-05 | 0 | 0 | 51 | 230 | 51 | 0 | 0 |  | PROJECT 1 A | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | 88 | [5 empty] | PROJECT 1 A | SKIMMER POND (4 UNIT) | 0.10434
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | CONTROL ROOM & BLOWER (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURCONTROL ROOM & BLOWER (4 unit) | LOW | Belum Mulai | 2025-02-10 | 2025-04-13 | 2025-04-12 | 0 | 2024-07-05 | 220 | 0 | 62 | -1 | 62 | -32 | 0.42275 | 0 | PROJECT 1 A | POWE HOUSE | 40 | [5 empty] | PROJECT 1 A | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | 0.081748
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | IPAL | PROJECT 1 A PEKERJAAN STRUKTURIPAL | MEDIUM | Dalam Proses | 2024-07-22 | 2025-05-11 | 2025-04-12 | 0.428 | 2024-07-05 | 17 | 125.404 | 167.596 | -29 | 293 | -4 | 0.74005 | 0.31674 | PROJECT 1 A | POWER HOUSE | -77 | [5 empty] | PROJECT 1 A | OPERATOR HOUSE (2 UNIT)‐ | 0.074967
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | NURSERY POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURNURSERY POND (4 unit) | LOW | Belum Mulai | 2024-12-16 | 2025-06-22 | 2025-04-12 | 0 | 2024-07-05 | 164 | 0 | 188 | -71 | 188 | 39 | 1.8989 | 0 | PROJECT 1 A | POWER HOUSE & WEEKLY TANK | -11 | [5 empty] | PROJECT 1 A | GALIAN & TIM BUNAN PIPA (4 AREA) | 0.067955
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | OPERATOR HOUSE (2 unit) | PROJECT 1 A PEKERJAAN STRUKTUROPERATOR HOUSE (2 unit) | LOW | Belum Mulai | 2025-02-10 | 2025-04-20 | 2025-04-12 | 0 | 2024-07-05 | 220 | 0 | 69 | -8 | 69 | -25 | 0.054312 | 0 | PROJECT 1 A | PROBIOTIK P[OND (4 UNIT) | -67 | [5 empty] | PROJECT 1 A | OPERATOR HOUSE (2 unit) | 0.054312
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | POND (12 unit) | PROJECT 1 A PEKERJAAN STRUKTURPOND (12 unit) | LOW | Terlambat | 2024-07-22 | 2025-06-22 | 2025-04-12 | 0.0121 | 2024-07-05 | 17 | 4.0535 | 330.9465 | -71 | 335 | 39 | 33.0584 | 0.40001 | PROJECT 1 A | PUMP HOUSE SWI | -67 | [5 empty] | PROJECT 1 A | PUPMP ROOM SWI | 0.049777
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | SKIMER POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURSKIMER POND (4 unit) | LOW | Belum Mulai | 2024-10-21 | 2025-02-16 | 2025-04-12 | 0 | 2024-07-05 | 108 | 0 | 118 | 55 | 118 | -88 | 0.61599 | 0 | PROJECT 1 A | PUPMP ROOM SWI | -95 | [5 empty] | PROJECT 1 A | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | 0.048862
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | SEA WATER INTAKE | SEA WATER INTAKE | PROJECT 1 A PEKERJAAN STRUKTURSEA WATER INTAKE | MEDIUM | Dalam Proses | 2024-09-23 | 2024-12-22 | 2025-04-12 | 0.4572 | 2024-07-05 | 80 | 41.148 | 48.852 | 111 | 90 | -144 | 1.4899 | 0.6812 | PROJECT 1 A | RESEARCH CENTRE ROOM | 39 | [5 empty] | PROJECT 1 A | OPERATOR HOUSE 1 s/d 2 | 0.043968
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DEEPWELL PUMP ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURDEEPWELL PUMP ROOM | LOW | Tunda | 2024-08-26 | 2025-01-26 | 2025-04-12 | 0 | 2024-07-05 | 52 | 0 | 153 | 76 | 153 | -109 | 0.020404 | 0 | PROJECT 1 A | RESEARCH CENTER ROOM | 35 | [5 empty] | PROJECT 1 A | DEEPWELL PUMP ROOM (DWP) | 0.03925
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ARSITEKTURPOWER HOUSE | LOW | Belum Mulai | 2025-01-20 | 2025-06-15 | 2025-04-12 | 0 | 2024-07-05 | 199 | 0 | 146 | -64 | 146 | 32 | 0.41565 | 0 | PROJECT 1 A | RESEARCH CENTER ROOM & SWI‐ | 81 | [5 empty] | PROJECT 1 A | RESERVOIR SEA WATER INTAKE | 0.035387
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE SWI | PROJECT 1 A PEKERJAAN ARSITEKTURPUMP HOUSE SWI | LOW | Belum Mulai | 2025-02-03 | 2025-03-09 | 2025-04-12 | 0 | 2024-07-05 | 213 | 0 | 34 | 34 | 34 | -67 | 0.023371 | 0 | PROJECT 1 A | RESERVOIR SEA WATER INTAKE | -67 | [5 empty] | PROJECT 1 A | PUMP HOUSE SWI | 0.023371
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURRESEARCH CENTER ROOM | LOW | Belum Mulai | 2025-05-12 | 2025-06-22 | 2025-04-12 | 0 | 2024-07-05 | 311 | 0 | 41 | -71 | 41 | 39 | 0.34221 | 0 | PROJECT 1 A | SEA WATER | -11 | [5 empty] | PROJECT 1 A | PROBIOTIK P[OND (4 UNIT) | 0.021883
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTURCONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | LOW | Belum Mulai | 2025-02-24 | 2025-04-20 | 2025-04-12 | 0 | 2024-07-05 | 234 | 0 | 55 | -8 | 55 | -25 | 0.22891 | 0 | PROJECT 1 A | SEA WATER INTAKE | -144 | [5 empty] | PROJECT 1 A | DEEPWELL PUMP ROOM | 0.020404
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | OPERATOR HOUSE (2 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTUROPERATOR HOUSE (2 UNIT)‐ | LOW | Belum Mulai | 2024-12-23 | 2025-04-13 | 2025-04-12 | 0 | 2024-07-05 | 171 | 0 | 111 | -1 | 111 | -32 | 0.074967 | 0 | PROJECT 1 A | SKIMER POND (4 unit) | -88 | [5 empty] | PROJECT 1 A | OPERATOR HOUSE (2 UNIT) | 0.014876
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | PROJECT 1 A PEKERJAAN ELEKTRIKALCONTROL ROOM & BLOWER HOUSE 1 s/d 4 | LOW | Belum Mulai | 2025-02-24 | 2025-04-27 | 2025-04-12 | 0 | 2024-07-05 | 234 | 0 | 62 | -15 | 62 | -18 | 0.081748 | 0 | PROJECT 1 A | SKIMMER POND (4 UNIT) | -95 | [5 empty] | PROJECT 1 A | DEEP WELL PUMP ROOM | 0.012092
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DEEP WELL PUMP ROOM | PROJECT 1 A PEKERJAAN ELEKTRIKALDEEP WELL PUMP ROOM | LOW | Belum Mulai | 2024-10-14 | 2025-03-09 | 2025-04-12 | 0 | 2024-07-05 | 101 | 0 | 146 | 34 | 146 | -67 | 0.012092 | 0 | PROJECT 1 A | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | 32 | [5 empty] | PROJECT 1 A | RESEARCH CENTRE ROOM | 0.0082318
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OPERATOR HOUSE 1 s/d 2 | PROJECT 1 A PEKERJAAN ELEKTRIKALOPERATOR HOUSE 1 s/d 2 | LOW | Belum Mulai | 2025-02-17 | 2025-03-09 | 2025-04-12 | 0 | 2024-07-05 | 227 | 0 | 20 | 34 | 20 | -67 | 0.043968 | 0 | PROJECT 1 A | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | -67 | [5 empty] | PROJECT 1 A | PEMBERSIHAN LAHAN | 0
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ELEKTRIKALPOWER HOUSE | LOW | Belum Mulai | 2024-12-23 | 2025-01-26 | 2025-04-12 | 0.1056 | 2024-07-05 | 171 | 3.5904 | 30.4096 | 76 | 34 | -109 | 2.2129 | 0.23368 | PROJECT 1 B | DORMITORY FEMALE | 281
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | RESEARCH CENTER ROOM & SWI‐ | PROJECT 1 A PEKERJAAN ELEKTRIKALRESEARCH CENTER ROOM & SWI‐ | LOW | Belum Mulai | 2025-03-17 | 2025-08-03 | 2025-04-12 | 0 | 2024-07-05 | 255 | 0 | 139 | -113 | 139 | 81 | 0.11597 | 0 | PROJECT 1 B | DORMITORY MALE | 417
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL | LOW | Belum Mulai | 2025-01-13 | 2025-06-29 | 2025-04-12 | 0.0478 | 2024-07-05 | 192 | 7.9826 | 159.0174 | -78 | 167 | 46 | 2.9188 | 0.13952 | PROJECT 1 B | FAMILY STAFF HOUSE | 475
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | GENERAL AREA POND | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL AREA POND | LOW | Belum Mulai | 2025-02-10 | 2025-05-11 | 2025-04-12 | 0.2191 | 2024-07-05 | 220 | 19.719 | 70.281 | -29 | 90 | -4 | 0.7164 | 0.15696 | PROJECT 1 B | FEED WAREHOUSE | 122
PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | PROJECT 1 A PEKERJAAN ELEKTRIKALPOND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | LOW | Belum Mulai | 2024-12-16 | 2025-08-10 | 2025-04-12 | 0 | 2024-07-05 | 164 | 0 | 237 | -120 | 237 | 88 | 2.7883 | 0 | PROJECT 1 B | GARDU HUB | 123
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY FEMALE | LOW | Terlambat | 2025-09-01 | 2025-08-24 | 2025-04-12 | 0 | 2024-08-01 | 396 | 0 | -8 | -134 | -8 | 102 | 0.65729 | 0 | PROJECT 1 B | GAZEBOO | 120
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY MALE | LOW | Terlambat | 2025-09-01 | 2025-09-30 | 2025-04-12 | 0 | 2024-08-01 | 396 | 0 | 29 | -171 | 29 | 139 | 2.2106 | 0 | PROJECT 1 B | GAZEBOO (BY VENDOR) | 53
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFAMILY STAFF HOUSE | LOW | Terlambat | 2025-09-22 | 2025-09-30 | 2025-04-12 | 0 | 2024-08-01 | 417 | 0 | 8 | -171 | 8 | 139 | 1.143 | 0 | PROJECT 1 B | GENERAL | 151
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFEED WAREHOUSE | LOW | Terlambat | 2025-07-07 | 2025-07-27 | 2025-04-12 | 0 | 2024-08-01 | 340 | 0 | 20 | -106 | 20 | 74 | 1.3022 | 0 | PROJECT 1 B | GUARD HOUSE 1 | 151
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ELEKTRIKALGARDU HUB | LOW | Belum Mulai | 2025-06-30 | 2025-07-13 | 2025-04-12 | 0 | 2024-08-01 | 333 | 0 | 13 | -92 | 13 | 60 | 0.45616 | 0 | PROJECT 1 B | GUARD HOUSE 2 | 604
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN ELEKTRIKALGAZEBOO | LOW | Belum Mulai | 2025-07-07 | 2025-08-03 | 2025-04-12 | 0 | 2024-08-01 | 340 | 0 | 27 | -113 | 27 | 81 | 0.8322 | 0 | PROJECT 1 B | GUARD TOWER | 32
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 1 | HIGH | Selesai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426 | 0 | 0 | 0 | PROJECT 1 B | GUEST HOUSE | 513
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 2 | LOW | Belum Mulai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0 | PROJECT 1 B | KANTIN | 366
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ELEKTRIKALKANTIN | LOW | Terlambat | 2025-08-25 | 2025-09-14 | 2025-04-12 | 0 | 2024-08-01 | 389 | 0 | 20 | -155 | 20 | 123 | 0.86889 | 0 | PROJECT 1 B | LABORATORIUM | 431
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ELEKTRIKALLABORATORIUM | LOW | Terlambat | 2025-09-01 | 2025-09-30 | 2025-04-12 | 0 | 2024-08-01 | 396 | 0 | 29 | -171 | 29 | 139 | 1.9102 | 0 | PROJECT 1 B | MAIN GATE | 167
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ELEKTRIKALMOSQUE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0 | PROJECT 1 B | MOSQUE | 604
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ELEKTRIKALOFFICE | LOW | Belum Mulai | 2025-07-07 | 2025-07-20 | 2025-04-12 | 0 | 2024-08-01 | 340 | 0 | 13 | -99 | 13 | 67 | 2.3615 | 0 | PROJECT 1 B | OFFICE | 268
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPUMP HOUSE | LOW | Terlambat | 2025-07-28 | 2025-08-24 | 2025-04-12 | 0 | 2024-08-01 | 361 | 0 | 27 | -134 | 27 | 102 | 1.1354 | 0 | PROJECT 1 B | PRIVATE HOUSE | 604
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALWEIGHT HOUSE | LOW | Terlambat | 2025-06-16 | 2025-06-29 | 2025-04-12 | 0 | 2024-08-01 | 319 | 0 | 13 | -78 | 13 | 46 | 0.9409 | 0 | PROJECT 1 B | PUMP HOUSE | 236
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ELEKTRIKALWORKSHOP | LOW | Terlambat | 2025-08-11 | 2025-08-31 | 2025-04-12 | 0 | 2024-08-01 | 375 | 0 | 20 | -141 | 20 | 109 | 1.2773 | 0 | PROJECT 1 B | TPS | 197
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALGUEST HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0 | PROJECT 1 B | VVIP HOUSE | 480
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPRIVATE HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0 | PROJECT 1 B | WATER TOWER 1 | 22
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALVVIP HOUSE | LOW | Belum Mulai | 2025-09-01 | 2025-09-21 | 2025-04-12 | 0 | 2024-08-01 | 396 | 0 | 20 | -162 | 20 | 130 | 1.1364 | 0 | PROJECT 1 B | WATER TOWER FACILITY AREA | 25
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY FEMALE | LOW | Dalam Proses | 2025-07-07 | 2025-05-31 | 2025-04-12 | 0.12519 | 2024-08-01 | 340 | -4.632 | -32.368 | -49 | -37 | 17 | 2.1434 | 0.26833 | PROJECT 1 B | WATER TOWER POND AREA | 25
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY MALE | LOW | Terlambat | 2025-06-30 | 2025-09-07 | 2025-04-12 | 0 | 2024-08-01 | 333 | 0 | 69 | -148 | 69 | 116 | 7.1456 | 0 | PROJECT 1 B | WEIGHT HOUSE | 180
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFAMILY STAFF HOUSE | LOW | Terlambat | 2025-07-07 | 2025-09-30 | 2025-04-12 | 0 | 2024-08-01 | 340 | 0 | 85 | -171 | 85 | 139 | 2.1434 | 0 | PROJECT 1 B | WORKSHOP | -95
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFEED WAREHOUSE | LOW | Terlambat | 2025-05-19 | 2025-06-06 | 2025-04-12 | 0 | 2024-08-01 | 291 | 0 | 18 | -55 | 18 | 23 | 2.6948 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ARSITEKTURGARDU HUB | LOW | Terlambat | 2025-06-02 | 2025-07-13 | 2025-04-12 | 0 | 2024-08-01 | 305 | 0 | 41 | -92 | 41 | 60 | 0.47544 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GAZEBOO (BY VENDOR) | PROJECT 1 BPEKERJAAN ARSITEKTURGAZEBOO (BY VENDOR) | LOW | Terlambat | 2025-06-23 | 2025-07-06 | 2025-04-12 | 0 | 2024-08-01 | 326 | 0 | 13 | -85 | 13 | 53 | 0.37058 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 1 | HIGH | Selesai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426 | 0 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 2 | LOW | Belum Mulai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ARSITEKTURKANTIN | LOW | Dalam Proses | 2025-06-16 | 2025-08-17 | 2025-04-12 | 0.17337 | 2024-08-01 | 319 | 10.7491 | 51.2509 | -127 | 62 | 95 | 2.1251 | 0.36843
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ARSITEKTURLABORATORIUM | LOW | Belum Mulai | 2025-07-21 | 2025-08-24 | 2025-04-12 | 0 | 2024-08-01 | 354 | 0 | 34 | -134 | 34 | 102 | 1.9262 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN ARSITEKTURMAIN GATE | LOW | Dalam Proses | 2025-06-16 | 2025-07-20 | 2025-04-12 | 0 | 2024-08-01 | 319 | 0 | 34 | -99 | 34 | 67 | 0.4509 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ARSITEKTURMOSQUE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ARSITEKTUROFFICE | LOW | Dalam Proses | 2025-06-16 | 2025-08-03 | 2025-04-12 | 0.14335 | 2024-08-01 | 319 | 6.8806 | 41.1194 | -113 | 48 | 81 | 4.2092 | 0.60337
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPUMP HOUSE | LOW | Terlambat | 2025-05-19 | 2025-07-27 | 2025-04-12 | 0 | 2024-08-01 | 291 | 0 | 69 | -106 | 69 | 74 | 0.46783 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN ARSITEKTURTPS | LOW | Terlambat | 2025-06-30 | 2025-08-31 | 2025-04-12 | 0 | 2024-08-01 | 333 | 0 | 62 | -141 | 62 | 109 | 0.6683 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURWEIGHT HOUSE | LOW | Belum Mulai | 2025-06-09 | 2025-07-27 | 2025-04-12 | 0 | 2024-08-01 | 312 | 0 | 48 | -106 | 48 | 74 | 0.67907 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ARSITEKTURWORKSHOP | LOW | Terlambat | 2025-06-23 | 2024-08-10 | 2025-04-12 | 0 | 2024-08-01 | 326 | 0 | -317 | 245 | -317 | -278 | 2.2141 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURGUEST HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPRIVATE HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURVVIP HOUSE | LOW | Terlambat | 2025-07-28 | 2025-09-30 | 2025-04-12 | 0 | 2024-08-01 | 361 | 0 | 64 | -171 | 64 | 139 | 7.4012 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY FEMALE | LOW | Terlambat | 2025-07-14 | 2025-07-20 | 2025-04-12 | 0 | 2024-08-01 | 347 | 0 | 6 | -99 | 6 | 67 | 0.15028 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY MALE | LOW | Terlambat | 2025-07-07 | 2025-07-27 | 2025-04-12 | 0 | 2024-08-01 | 340 | 0 | 20 | -106 | 20 | 74 | 0.53564 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALFAMILY STAFF HOUSE | LOW | Terlambat | 2025-07-28 | 2025-08-17 | 2025-04-12 | 0 | 2024-08-01 | 361 | 0 | 20 | -127 | 20 | 95 | 0.15028 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 1 | LOW | Terlambat | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 2 | LOW | Terlambat | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN MEKANIKALKANTIN | LOW | Terlambat | 2025-07-14 | 2025-08-03 | 2025-04-12 | 0 | 2024-08-01 | 347 | 0 | 20 | -113 | 20 | 81 | 0.31366 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN MEKANIKALLABORATORIUM | LOW | Belum Mulai | 2025-07-28 | 2025-09-07 | 2025-04-12 | 0 | 2024-08-01 | 361 | 0 | 41 | -148 | 41 | 116 | 0.1253 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN MEKANIKALMOSQUE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN MEKANIKALOFFICE | LOW | Terlambat | 2025-06-23 | 2025-07-06 | 2025-04-12 | 0 | 2024-08-01 | 326 | 0 | 13 | -85 | 13 | 53 | 0.16406 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER FACILITY AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER FACILITY AREA | LOW | Terlambat | 2025-05-26 | 2025-06-08 | 2025-04-12 | 0 | 2024-08-01 | 298 | 0 | 13 | -57 | 13 | 25 | 0.41311 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER POND AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER POND AREA | LOW | Terlambat | 2025-05-26 | 2025-06-08 | 2025-04-12 | 0 | 2024-08-01 | 298 | 0 | 13 | -57 | 13 | 25 | 0.41311 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALGUEST HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALPRIVATE HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALVVIP HOUSE | LOW | Belum Mulai | 2025-08-04 | 2025-08-24 | 2025-04-12 | 0 | 2024-08-01 | 368 | 0 | 20 | -134 | 20 | 102 | 0.71591 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY FEMALE | MEDIUM | Dalam Proses | 2025-04-28 | 2025-08-17 | 2025-04-12 | 0.3123 | 2024-08-01 | 270 | 34.665 | 76.335 | -127 | 111 | 95 | 1.2317 | 0.38466
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY MALE | LOW | Dalam Proses | 2024-10-28 | 2025-08-10 | 2025-04-12 | 0.07166 | 2024-08-01 | 88 | 20.4948 | 265.5052 | -120 | 286 | 88 | 4.3412 | 0.31109
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN STRUKTURFAMILY STAFF HOUSE | LOW | Dalam Proses | 2025-04-21 | 2025-08-24 | 2025-04-12 | 0.071875 | 2024-08-01 | 263 | 8.9844 | 116.0156 | -134 | 125 | 102 | 1.2842 | 0.092304
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN STRUKTURFEED WAREHOUSE | LOW | Dalam Proses | 2025-04-15 | 2025-06-08 | 2025-04-12 | 0.23927 | 2024-08-01 | 257 | 12.9203 | 41.0797 | -57 | 54 | 25 | 7.3157 | 1.7504
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN STRUKTURGARDU HUB | LOW | Dalam Proses | 2025-04-15 | 2025-05-17 | 2025-04-12 | 0.1104 | 2024-08-01 | 257 | 3.5327 | 28.4673 | -35 | 32 | 3 | 0.87756 | 0.09688
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN STRUKTURGAZEBOO | LOW | Terlambat | 2025-06-02 | 2025-06-22 | 2025-04-12 | 0.16107 | 2024-08-01 | 305 | 3.2215 | 16.7785 | -71 | 20 | 39 | 0.012874 | 0.0020737
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 1 | HIGH | Selesai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 100% | 2024-08-01 | 11 | 426 | 0 | -183 | 426 | 0 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 2 | LOW | Belum Mulai | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD TOWER | PROJECT 1 BPEKERJAAN STRUKTURGUARD TOWER | MEDIUM | Dalam Proses | 2025-04-21 | 2025-06-15 | 2025-04-12 | 0.28551 | 2024-08-01 | 263 | 15.7029 | 39.2971 | -64 | 55 | 32 | 0.90362 | 0.25799
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN STRUKTURKANTIN | MEDIUM | Dalam Proses | 2025-04-21 | 2025-07-20 | 2025-04-12 | 0.43399 | 2024-08-01 | 263 | 39.0592 | 50.9408 | -99 | 90 | 67 | 1.5819 | 0.68652
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN STRUKTURLABORATORIUM | LOW | Dalam Proses | 2025-04-15 | 2025-07-27 | 2025-04-12 | 0.08637 | 2024-08-01 | 257 | 8.8961 | 94.1039 | -106 | 103 | 74 | 1.2678 | 0.1095
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN STRUKTURMAIN GATE | LOW | Dalam Proses | 2025-04-28 | 2025-08-22 | 2025-04-12 | 0 | 2024-08-01 | 270 | 0 | 116 | -132 | 116 | 100 | 0.35948 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN STRUKTURMOSQUE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0% | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN STRUKTUROFFICE | MEDIUM | Dalam Proses | 2025-04-15 | 2025-07-20 | 2025-04-12 | 0.40779 | 2024-08-01 | 257 | 39.148 | 56.852 | -99 | 96 | 67 | 3.3921 | 1.3833
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPUMP HOUSE | LOW | Dalam Proses | 2025-05-05 | 2025-07-13 | 2025-04-12 | 0.099325 | 2024-08-01 | 277 | 6.8534 | 62.1466 | -92 | 69 | 60 | 0.94074 | 0.093439
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN STRUKTURTPS | LOW | Dalam Proses | 2025-05-05 | 2025-08-10 | 2025-04-12 | 0.062209 | 2024-08-01 | 277 | 6.0343 | 90.9657 | -120 | 97 | 88 | 1.1565 | 0.071947
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | LOW | Belum Mulai | 2025-05-05 | 2025-05-25 | 2025-04-12 | 0.17438 | 2024-08-01 | 277 | 3.4875 | 16.5125 | -43 | 20 | 11 | 0.90362 | 0.15757
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | LOW | Terlambat | 2025-05-05 | 2025-05-25 | 2025-04-12 | 0.17438 | 2024-08-01 | 277 | 3.4875 | 16.5125 | -43 | 20 | 11 | 0.90362 | 0.15757
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN STRUKTURWEIGHT HOUSE | MEDIUM | Dalam Proses | 2025-05-05 | 2025-07-13 | 2025-04-12 | 0.3074 | 2024-08-01 | 277 | 21.2107 | 47.7893 | -92 | 69 | 60 | 5.6464 | 1.7357
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN STRUKTURWORKSHOP | HIGH | Dalam Proses | 2025-04-28 | 2025-07-27 | 2025-04-12 | 0.79925 | 2024-08-01 | 270 | 71.9326 | 18.0674 | -106 | 90 | 74 | 6.1842 | 4.9427
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 BPEKERJAAN STRUKTURGENERAL | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | (blank) | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN STRUKTURGUEST HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-07-13 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 335 | -92 | 335 | 60 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPRIVATE HOUSE | LOW | Dalam Proses | 2024-08-12 | 2025-10-12 | 2025-04-12 | 0 | 2024-08-01 | 11 | 0 | 426 | -183 | 426 | 151 | 0 | 0
PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURVVIP HOUSE | LOW | Terlambat | 2025-04-15 | 2025-08-31 | 2025-04-12 | 0.088536 | 2024-08-01 | 257 | 12.218 | 125.782 | -141 | 138 | 109 | 7.3681 | 0.65234
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Help (hidden)
HELP
About
This task list template shows how you can create a gantt chart as a stacked bar chart in Excel. The Project Start date is the first series in the chart, but it is shown as a hidden bar by changing the fill color to None. The Minimum bound for the x-axis should be set to the Project Start date (and that is a manual process - see below).
Adjust the Minimum Bound for the X-axis
When you change the Project Start date, you will need to also update the Minimum bound for the X-axis in the gantt chart. Right-click on the x-axis labels in the chart and go to Format Axis.
Adding More Rows
When you insert new rows, you should insert a blank row, then copy formulas down in the columns with the gray background.
Conditional Formatting
The Priority column uses conditional formatting to highlight cells differently based on their text value. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.